## Agenda
| #VALUE! |  | #VALUE!
Collaborative: | Northwest Collaborative Planning & Implementation Group
Meeting Type: | Monthly Collaborative Convening
Date: | Tuesday, March 19, 2024 | Location: | Northwest Zoom Link
Time: | 01:00 – 2:00 PM | Facilitator: | Population Health Innovation Lab, Public Health Institute
High Level Agenda
| Topic | Key Questions
Welcome, Framing, & Check-In
| Local Organization Spotlight | What lessons can be learned from the experiences of local organizations that have successfully overcome challenges with ECM or Community Supports referrals and authorizations?
| Policy Briefs | What are the highlights from recent Department of Health Care Services policy updates that may inform work as local CalAIM providers?
| Update from Partnership HealthPlan of California | What updates from PHC will impact existing and prospective ECM and Community Supports workflow processes?
| Strengthening CalAIM Referral Pathways in the Ecosystem of Care | What current practices or innovations contribute to strong referrals and caseloads in the region? How might local organizations leverage the no-wrong-door referral policy to strengthen local collaboration, support care coordination, and enhance ECM and CS services?
Northwest CPI Updates and Upcoming Events
Evaluation & Close
New Action Items (Identified this Meeting)
No. | Action Item | Owner | Created | Deadline | Status
1. | Meet with NCHIIN and Humboldt 211, which support local servcie provider information and referral networks, to explore how they might strengthen knowledge and informaton sharing across local organizations in order to increase CalAIM community-based referrals and service utilization. | Program Manager | 2024-03-25 | 2023-04-30 | Incomplete
| Monitor referral progress to determine if additional community-based and provider referrals follow increased knowledge/awareness. | Program Manager with support of MERLIN | 2024-03-26 | Continuous | Incomplete
2. | Adjust the timing of monthly meetings based on participants' preferences. | Program Associate II | 2024-03-22 | 2023-04-15 | Incomplete
Open Action Items
No. | Action Item | Owner | Created | Deadline | Status
1 | Integrate the issue of confident and confidential care coordination into future programming. | Program Associate II and Program Manager | 2024-02-27 | 2024-05-01 | Incomplete
2 | Evaluate and explore the notion of feasibility, sustainability and braided funding in upcoming Northwest PATH CPI Programming | Program Manager | 2024-02-27 | 2024-05-01 | Incomplete
3 | Coordinate with Camden Coalition on when to debut the "Go, No Go Feasibility Tool" | Program Associate II | 2024-02-27 | 2024-03-10 | Pending
4 | Follow up with Action Items identified during the Ecosystems Activity | CPI participants with Program Manager support | 2024-02-27 | 2024-03-15 | Partially complete and in progress
5 | Several questions emerged about Administrative Hubs/Care Hubs – policy follow up with PHC, PCG/DHCS to inform future CPI participant trainings. | Program Manager | 2024-02-27 | 2024-03-10 | Completed
6 | Invite K'ima:w Medical Center as a spotlight organization so they could share more abour their journey to becoming a ECM and Community Supports provider. | Program Associate II | 2024-02-27 | 2024-03-10 | Pending
7 | Follow up with Native Spirit Consulting to learn how PHIL could be of support and service to organizations interestested in participating in CalAIM. | Program Associate II and Program Manager | 2024-02-27 | 2024-03-10 | Completed
8 | Begin program development of the "Administrative Burden" Test of Change. This includes conducting a landscape assessment to learn the general understanding of hub models and glean regional interest. | Program Manager | 2024-01-26 | 2024-04-20 | Incomplete
9 | Schedule meeting with NCHIIN and Arcata House to learn about the pilot program. | PHIL | 11/15/2023 | 3/30/2024 | Incomplete
Ongoing Action Items
No. | Action Item | Owner | Created | Deadline | Status
1 | Integrate tools for sustainability through the upcoming convenings, resources and conversations. | PHIL | 8/28/2023 | Continuous | Ongoing
2 | Integrate updated tools and resources in the Pre-Contract and Post-Contract Process, Tools, and Solutions packet. Share updates with collaboratives and CPI Facilitators as they become available. | PHIL | 8/28/2023 | Continuous | Ongoing
3 | Follow up with organizations who show great and minimal progress along the Readiness Roadmap for support and guidance. | PHIL | 6/29/2023 | Continuous | Strategizing
4 | Re-vamp website with developing resource and information needs to continue serving current and prospective CPI participants | PHIL | 5/30/2023 | Continuous | Implementing
5 | Develop collaborative systems improvement strategies. | PHIL | 4/21/2023 | Continuous | Strategizing
6 | Identify specific capacity building training. | PHIL | 4/21/2023 | Continuous | Outlined and finalizing
7 | Network and relationship building with new members added to the asset maps. | PHIL | 4/21/2023 | Continuous | Strategizing
8 | Identify existing coalitions, collaboratives and roundtables for ECM, Community supports | PHIL and CPI Partners | 3/30/2023 | Continuous | Data synthesized by mapping project will help to identify these initiatives.
9 | Recruitment of new CPI participants | PHIL and CPI Partners | 1/1/2023 | Continuous | Implementing
Closed Action Items
No. | Action Item | Owner | Created | Deadline | Status
1 | Revise the Theory of Change and share updates with the Northwest CPI Collaborative. | Program Associate II | 2024-02-27 | 2024-03-10 | Complete
2 | Follow up with Arcata House Partnership to learn how they are increasing clients, as some organizations are having difficulty with receiving referrals and large enough case loads to be sustainable. | Program Associate II | 2024-02-27 | 2024-03-10 | Complete
3 | PHIL will develop and distribute a flyer that shares an overview of CPI Facilitators Required Activities, as well as contact information for the programs administrators. This will be distributed as an email to the convenings attendants, and will be shared on the PATH CPI website. | Program Associate II | 2024-01-24 | 2024-01-29 | Complete
4 | PHIL will develop and distribute an "Action Lever Reference Guide" that shares an overview of DHCS Action Levers. This will be distributed as an email to the convenings attendants, and will be shared on the PATH CPI website. | Program Manager | 2024-01-25 | 2024-01-29 | Complete
5 | Develop a Q&A document for questions that were not answered. Once answered, the Q&A document will be sent to participants and will be added to the Readiness Roadmap website. | PHIL | 12/05/2023 | 12/15/2023 | Completed
6 | Ask Open Door Community Health Centers if we can share their CHW workflow. | PHIL | 12/05/2023 | 12/15/2023 | Completed
7 | Coordinate a conversation with PHC to learn how they can deliver updates regarding Birth Equity. | PHIL | 12/05/2023 | 12/15/2023 | Incomplete
8 | Support conversations between local HIE and DHCS to learn more about the “Closed Loop Referral System”. | PHIL | 12/05/2023 | 12/15/2023 | Complete
9 | Learn how HealthBegins is supporting their collaboratives with Case Consulting. | PHIL | 11/01/2023 | 11/15/2023 | Complete
10 | Uplift provider concerns DHCS’ marketing strategies for ECM and CS. | PHIL | 11/01/2023 | 11/15/2023 | Complete
11 | Issue Tracker additions: | PHIL | 8/28/2023 | 9/15/2023 | Completed
- Accessibility to tools from PHC including z codes, g code sheets, and eligible participant lists.
- ECM and/or CS implementation barriers unique to school-based clinics.
12 | Mapping care coordination processes. | PHIL | 6/29/2023 | 8/5/2023 | No longer a priority of the collaborative
13 | Propose monthly meetings with Camden, HC2, HealthBegins and Partnership to efficiently collate common issues among CPI collaboratives across Northern California counties | PHIL | 5/30/2023 | 6/5/2023 | Completed
14 | Strategize methods of collecting the step all participants are at on the Readiness Roadmap (polled during meetings as well as follow-up conversations) | PHIL | 4/21/2023 | 5/5/2023 | Completed
15 | A report of the initial Asset Mapping Survey findings is to be shared with the participants on the website. | MERLIN | 4/21/2023 | 6/5/2023 | Completed
16 | Incorporating charter feedback | PHIL | 1/1/2023 | 3/31/2023 | Completed
17 | PATH CPI Asset Mapping Survey | PHIL | 1/1/2023 | 5/15/2023 | Completed

## Meeting Summary
Key Takeaways & Discussion Themes by Agenda Topic
Topic | Discussion Themes/Key Takeaways | Actions Taken/Next Steps | Best Practices/Lessons Learned
Welcome, Framing, & Check-In | N/A | N/A | N/A
Local Organization Spotlight | Discussion Themes: Proactive Engagement: Rather than passively waiting for referrals, there's a willingness to directly reach out to individuals (1:1) who may benefit from services. Taking the initiative to establish and nurture relationships within networks, emphasizing the value of proactive engagement. Importance of Relationships and Networking: Recognizing the significance of strong interpersonal connections and networks in facilitating referrals and support. Key Takeaways: Arcata House Partnership and Adult Day Health Care of Mad River were invited to the convening to share their successful establishment of communication and a collaborative relationship as local ECM and Community Supports providers. In addition to detailing their respective strategies for generating referrals, they detailed the importance of effectively coordinating referrals to ensure optimal support for clients. Referrals are generated via telephonic outreach, internal referrals and by the MCP. | N/A | N/A
Policy Briefs | Key Takeaways: PHIL shared recent Department of Health Care Services Policy Updates including: - Updates for the ECM Policy Guide - Update on County-Based Targeted Case Management (TCM) & ECM - Dual-Eligable Members - Use of Data to Monitor ECM: HCPCS - Link for ECM for Individuals and Families Experiencing Homelessness Spotlight - Update on 2024 Update ECM referral and authorization standards | Actions Taken: - The policy update resources are added to the "Shared Collaborative Resources" section below. | N/A
Update from Partnership HealthPlan of California | Key Takeaways: - Partnership HealthPlan of California has developed 2024-2025 CalAIM grants to invest in Enhanced Care Management (ECM) and Community Supports (CS) providers. Grants are open to all ECM and CS providers in Partnership's 24 counties. - PHC will be hosting a CalAIM Grant Program Informational Webinar on April 3, 2024. | Actions Taken: - The PHC flyer for the CalAIM Grant Program Informational Webinar is linked in the "Shared Collaborative Resources" section below. | N/A
Strengthening CalAIM Referral Pathways in the Ecosystem of Care | Discussion themes: Inter-Agency Communication to increase referrals and CalAIM authorization opportunities, as well as strengthen community based coordinated care: Communication within and across Del Norte and Humboldt County agencies can increase referrals for CalAIM services, get existing individuals additional services they need, and can help facilitate coordinated care across the county's expansive landscape, indicating a collaborative effort to address the diverse needs of residents. Challenges of Rural Isolation and Cross-Coordination: Recognition of the obstacles posed by the isolated geography of rural areas, necessitating cross-coordination efforts between rural communities and larger cities to ensure equitable access to services and resources. Impact of Trusted Provider Relationships: Highlight the significance of established trust between local providers in facilitating effective care coordination, contrasting with decreased confidence in care coordination when clients are referred to other unknown providers. Limited Housing Availability and Referral Patterns: Note the influence of limited housing availability in rural areas, leading to referrals of clients to more populous areas, which in turn complicates care coordination due to geographical distance and potential resource disparities. | Next Steps: Meet with NCHIIN and Humboldt 211, which support local servcie provider information and referral networks, to explore how they might strengthen knowledge and informaton sharing across local organizations in order to increase CalAIM community-based referrals and service utilization. Actions Taken: - The presentation and discussion referenced the January 30th PHC Webinar on on ECM and Community supports Referral Sources. The full PHC presentation and Chat Q&A document is linked in the "Shared Collaborative Resources" section below. | Contracted providers seem to anticipate generating CalAIM referrals primarily from their existing client base, underscoring the importance of strengthening internal referral processes and engagement with clients regarding CalAIM services as well as strengthening knowledge and referral information across local organizations that are part of the CalAIM Ecosystem of Care. Referral Poll: 1. Where do you refer people who are Medi-Cal eligible for CalAIM services? (check all that apply □ My organization (7/9, 78%) □ Other local organizations. (2/9, 22%) □ Anywhere I can in the CalAIM provider network. (1/9, 11%) □ I do not currently refer Medi-Cal Members to CalAIM services. (2/9, 22%) 2. If you are a contracted provider/or plan to be a contracted provider, where do you expect most of your CalAIM referrals to come from this year? □ Existing client based within my organization. (6/9, 67%) □ Other local organizations (1/9, 11%) □ From our Medi-Cal Managed Care Plan's member referral process (1/9, 11%) Other (1/9, 11%)
Northwest CPI Updates and Upcoming Events | Key Takeaways: - PHIL anticipates sharing the Camden Coalition CalAIM Revenue Estimator & Budget Tool when it becomes available. - The Theory of Change visual has been updated! - Multiple TA Marketplace Vendor Fairs are scheduled in the upcoming weeks. | Actions Taken: - The updated Theory of Change visual is linked in the "Shared Collaborative Resources" section below. - Registration links for all upcoming TA Marketplace Vendor Fairs are linked in the "Shared Collaborative Resources" section below. | N/A
Evaluation & Close | N/A | N/A | N/A
Identified Gaps/Challenges in CalAIM/ECM/Community Supports
Topic | Gaps/Challenges Identified | Actions Taken/Next Steps | Best Practices/Lessons Learned
ECM and Community Supports Uptake | Slow ECM and Community Supports uptake in the region brings forth challenges, such as difficulties to refer to alternative providers that are close in proximity and quality. | N/A | N/A
ECM and Community Supports Uptake | Very few local contracted (and not contracted) providers. | N/A | N/A
Information Resource Access | Lack of quality service information resources that are updated with ECM and Community Supports providers. | N/A | N/A
Rural Services | The rural nature of the Northwest region has posed significant challenges for the expansion of ECM and community support services, including difficulties in facilitating referrals and enhancing accessibility of local providers. | N/A | N/A
Identified Successes Experienced by Participants
Topic | Successes Identified | Actions Taken/Next Steps | Best Practices/Lessons Learned
Referrals | Local organizations are fostering stronger, more intimate connections among themselves. Through established channels of communication, they are gaining a deeper understanding of each other's service capabilities and effectively utilizing specialized services. | N/A | Lessons Learned: Establishing relationships with organizations through direct communication can enhance the quality and efficiency of referrals, thereby improving timely access to healthcare services for clients.
Referrals | The uplifting success of coordinated referrals at the local level has heightened awareness regarding how organizations can initiate quality referrals. | Next Steps: Monitor referral progress to determine if additional community-based and provider referrals follow increased knowledge/awareness. | N/A
Summary of Complaints & Grievances
Topic | Summary of Complaint/Grievance | Actions Taken | Next Steps
N/A | N/A | N/A | N/A
MCP Engagement (List all MCPs who should be engaged regardless of attendance) |  |  |  | KEY
MCP Name | Current Status of Relationship | MCP Engagement in Collaborative | Engagement Concerns & Notes | Acceptable | MCP attends 50%-75% collaborative convenings, MCP is responsive to collaborative requests but follow up is needed by facilitator
| i.e. Excellent > Acceptable > Needs Improvement > In Direct Contact With > No Contact | Yes/No |  | Excellent | MCP is engaged in collaborative, MCP attends 75%-100% collaborative convenings, MCP is presenter during collaborative meetings, MCP provides feedback and data where applicable, MCP works in partnership with facilitator and collaborative
Partnership HealthPlan of California | Excellent | Yes | PHC delivered a concise and informative presentation during this month's collaborative session. They demonstrated knowledgeable responses to inquiries and maintained a positive presence throughout the interaction. | In Direct Contact With | Facilitator has direct contact with MCP, MCP may not currently be attending collaboratives, MCP may be transitioning in 2024 and not yet active in collaborative
|  |  |  | Needs Improvement | MCP is not or inconsistently engaged in collaborative, MCP attends 0%-25% of collaborative convenings, difficulties consulting with MCP, further partnership and relationship building is required
|  |  |  | No Contact | There is no contact with MCP, MCP is not present for collaborative meetings, no relationship built with MCP
Shared Collaborative Resources
Resource | Category/Type | Link/Access Information
PATH CPI | Website | https://pophealthinnovationlab.org/projects/path/
Native Lands | Website | https://native-land.ca
Arcata House Partnership | Website | https://www.arcatahouse.org/.
ECM Policy Guide | PDF | https://www.dhcs.ca.gov/CalAIM/ECM/Documents/ECM-Policy-Guide.pdf
Enhanced Care Management for Individuals Experiencing Homelessness: A Population of Focus Spotlight | Website | https://bit.ly/3VqKBw8
Partnership HealthPlan of California's CalAIM Grant Program Informational Webinar | Flyer | https://bit.ly/4cmWn0x
Partnership HealthPlan of California ECM Roundtable | Webinar | https://bit.ly/4cmy8Q2
Partnership HealthPlan of California Community Supports Roundtable | Webinar | https://bit.ly/3vhc34b
Updated Theory of Change for the Northwest Collaborative | PDF | https://bit.ly/43sYGv5
Northwest CPI Collaborative Convenings: | Registration Link | https://bit.ly/4a7MW3G
Northwest CPI Collaborative Office Hours Wednesdays: | Registration Link | https://bit.ly/3TKzMDW
Northwest CPI Collaborative Office Hours Mondays: | Registration Link | https://bit.ly/4a1iGan
TA Marketplace Vendor Fair Events- Domain 1: Building Data Capacity | Registration Links | https://bit.ly/3THlh3E
TA Marketplace Vendor Fair Events- Domain 2: Community Supports and Domain 7: Workforce | Registration Links | https://bit.ly/3x1vzTf
TA Marketplace Vendor Fair Events- Domain 5 and Domain 6: Supporting Cross-Sector Partnership | Registration Links | https://bit.ly/499GTtL
Partnership HealthPlan of California's 2024 ECM/CS Provider Referral Source Webinar Q&A | PDF | Q&A Document
Partnership HealthPlan of California's Enhanced Care Management and Community Supports: Referral Source Webinar | PDF | Webinar Slides
PATH CPI Survey Link | Survey Link | https://bit.ly/4ajenak

## Meeting Attendance
Note: If your office hours were combined with another collaborative or facilitator group, please complete columns D & E.
Organization Name | Participant Name | Email | Collaborative Group | Facilitator Group
Humboldt County Public Health | Aaron Wythe | awythe@co.humboldt.ca.us | Northwest | Population Health Innovation Lab, Public Health Institute
Humboldt County Public Health | Aaron Zell | azell@co.humboldt.ca.us | Northwest | Population Health Innovation Lab, Public Health Institute
Arcata House Partnership | Alissa Smith | asmith@arcatahouse.org | Northwest | Population Health Innovation Lab, Public Health Institute
Adult Day Health Care of Mad River | April Joyce | ajoyceadhc@gmail.com | Northwest | Population Health Innovation Lab, Public Health Institute
Partnership HealthPlan of CA | Ashley Peel | apeel@partnershiphp.org | Northwest | Population Health Innovation Lab, Public Health Institute
North Coast Health Improvement and Information Network | Chris Davis | cdavis@nchiin.org | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Esmeralda Salas | esalas@phi.org | Northwest | Population Health Innovation Lab, Public Health Institute
North Coast Health Improvement and Information Network | Jessica Osborne-Stafsnes | josborne@nchiin.org | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Jessica Sanchez | jsanchez2@phi.org | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Kathryn Stewart | kastewart@phi.org | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Katie Christian | kchristian@phi.org | Northwest | Population Health Innovation Lab, Public Health Institute
BALANCE Financial Empowerment | Lara Brecher | lbrecher@balancepro.org | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Megan Kenney | mkenney@phi.org | Northwest | Population Health Innovation Lab, Public Health Institute
Redwoods Rural Health Center | Michele Hernandez | mhernandez@rrhc.org | Northwest | Population Health Innovation Lab, Public Health Institute
Humboldt County Public Health | Morgan Brannon | mbrannon@co.humboldt.ca.us | Northwest | Population Health Innovation Lab, Public Health Institute
Partnership HealthPlan of CA | Paola De La Cruz | pdelacruz@partnershiphp.org | Northwest | Population Health Innovation Lab, Public Health Institute
Open Door | Sandra Miliotti | smiliotti@opendoorhealth.com | Northwest | Population Health Innovation Lab, Public Health Institute
Roots Food Grop | Sara Tindaro | sara@rootsfoodgroup.com | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Seun Aluko | seun@pophealthinnovationlab.org | Northwest | Population Health Innovation Lab, Public Health Institute
Shari Brenner Health Systems Consulting | Shari Brenner | sbrenner@sonic.net | Northwest | Population Health Innovation Lab, Public Health Institute
St. Joe's | Sharon Hunter | sharon.hunter@stjoe.org | Northwest | Population Health Innovation Lab, Public Health Institute
Hartsfield Consulting | Stefani Hartsfield | stefani@hartsfieldhealth.com | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Sue Grinnell | sgrinnell@phi.org | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Tammy Chandler | tchandler@phi.org | Northwest | Population Health Innovation Lab, Public Health Institute
Arcata House Partnership | Virginia Beckman | vbeckman@arcatahouse.org | Northwest | Population Health Innovation Lab, Public Health Institute
Native Spirit Consulting | Zachary Ray | zray@nativespiritconsulting.com | Northwest | Population Health Innovation Lab, Public Health Institute
14803299322 | Unknown | Unknown | Northwest | Population Health Innovation Lab, Public Health Institute
17078634418 | Unknown | Unknown | Northwest | Population Health Innovation Lab, Public Health Institute

## Lists (hidden)
Meeting Type
Monthly Collaborative Convening
Office Hours