## Agenda
| #VALUE! |  | #VALUE!
Collaborative: | Northwest Collaborative Planning & Implementation Group
Meeting Type: | Monthly Collaborative Convening
Date: | Tuesday, April 16, 2024 | Location: | Zoom Link
Time: | 1:00 – 2:00 PM | Facilitator: | Population Health Innovation Lab, Public Health Institute
High Level Agenda
| Topic | Key Questions
Welcome, Framing, & Check-In
| Local Organization Spotlight | What lessons can be learned from the experiences of local organizations that have successfully implemented new CalAIM revenue streams?
| Utilization Data Informed Goals | How can utilization trends over the past year inform our current work and our goals for the year?
| Update from Partnership HealthPlan of California | What updates from PHC will impact existing and prospective ECM and Community Supports processes?
| Spotlight on CalAIM Program and Revenue Enhancement Strategies | How can PHC’s ECM Quality Improvement Program (QIP) strengthen program services and generate revenue? What is the current CalAIM funding landscape and how can organizations leverage these opportunities?
| PATH CPI Updates and Upcoming Events | How can Office Hours and Regional Workgroups strengthen local CalAIM ECM and Community Support services?
Evaluation & Close
New Action Items (Identified this Meeting)
No. | Action Item | Owner | Created | Deadline | Status
1. | Coordinate with COTS to collect and share workplans, processes, and templates developed for their QIP program to CPI Participants via the PATH CPI website. | Program Associate II | 2024-04-22 | 2024-04-22 | Pending
2. | Continue the core work of the PATH CPI initiative to outreach and support CalAIM contract development, strengthen community-based referral, and monitor access to and utilization of CalAIM services. | PHIL | 2024-04-22 | Continuous | Ongoing
3. | Coordinate with Partnership HealthPlan to co-facilitate a training for their QIP program measurements, dependent on the needs of participants. (See Lessons Learned) | Program Manager and Program Associate II | 2024-04-22 | 2024-05-03 | Incomplete
Open Action Items
No. | Action Item | Owner | Created | Deadline | Status
1 | Meet with NCHIIN and Humboldt 211, which support local service provider information and referral networks, to explore how they might strengthen knowledge and informaton sharing across local organizations in order to increase CalAIM community-based referrals and service utilization. | Program Manager | 2024-03-25 | 2023-04-30 | Incomplete
2 | Integrate the issue of confident and confidential care coordination into future programming. | Program Associate II and Program Manager | 2024-02-27 | 2024-05-01 | Incomplete
3 | Follow up with Action Items identified during the Ecosystems Activity | CPI participants with Program Manager support | 2024-02-27 | 2024-03-15 | Partially complete and in progress
4 | Invite K'ima:w Medical Center as a spotlight organization so they could share more abour their journey to becoming a ECM and Community Supports provider. | Program Associate II | 2024-02-27 | 2024-03-10 | Pending response
5 | Begin program development of the "Administrative Burden" Test of Change. This includes conducting a landscape assessment to learn the general understanding of hub models and glean regional interest. | Program Manager | 2024-01-26 | 2024-04-20 | In Progress
6 | Schedule meeting with NCHIIN and Arcata House to learn about the pilot program. | PHIL | 11/15/2023 | 3/30/2024 | Incomplete
Ongoing Action Items
No. | Action Item | Owner | Created | Deadline | Status
1 | Monitor referral progress to determine if additional community-based and provider referrals follow increased knowledge/awareness. | Program Manager with support of MERLIN | 2024-03-26 | Continuous | Ongoing
2 | Integrate tools for sustainability through the upcoming convenings, resources and conversations. | PHIL | 8/28/2023 | Continuous | Ongoing
3 | Integrate updated tools and resources in the Pre-Contract and Post-Contract Process, Tools, and Solutions packet. Share updates with collaboratives and CPI Facilitators as they become available. | PHIL | 8/28/2023 | Continuous | Ongoing
4 | Follow up with organizations who show great and minimal progress along the Readiness Roadmap for support and guidance. | PHIL | 6/29/2023 | Continuous | Strategizing
5 | Re-vamp website with developing resource and information needs to continue serving current and prospective CPI participants | PHIL | 5/30/2023 | Continuous | Implementing
6 | Develop collaborative systems improvement strategies. | PHIL | 4/21/2023 | Continuous | Strategizing
7 | Identify specific capacity building training. | PHIL | 4/21/2023 | Continuous | Outlined and finalizing
8 | Network and relationship building with new members added to the asset maps. | PHIL | 4/21/2023 | Continuous | Strategizing
9 | Identify existing coalitions, collaboratives and roundtables for ECM, Community supports | PHIL and CPI Partners | 3/30/2023 | Continuous | Data synthesized by mapping project will help to identify these initiatives.
10 | Recruitment of new CPI participants | PHIL and CPI Partners | 1/1/2023 | Continuous | Implementing
Closed Action Items
No. | Action Item | Owner | Created | Deadline | Status
1 | Adjust the timing of monthly meetings based on participants' preferences. | Program Associate II | 2024-03-22 | 2023-04-15 | Complete
2 | Evaluate and explore the notion of feasibility, sustainability and braided funding in upcoming Northwest PATH CPI Programming | Program Manager | 2024-02-27 | 2024-05-01 | Completed
3 | Coordinate with Camden Coalition on when to debut the "Go, No Go Feasibility Tool" | Program Associate II | 2024-02-27 | 2024-03-10 | Complete
4 | Several questions emerged about Administrative Hubs/Care Hubs – policy follow up with PHC, PCG/DHCS to inform future CPI participant trainings. | Program Manager | 2024-02-27 | 2024-03-10 | Completed
5 | Follow up with Native Spirit Consulting to learn how PHIL could be of support and service to organizations interestested in participating in CalAIM. | Program Associate II and Program Manager | 2024-02-27 | 2024-03-10 | Completed
6 | Revise the Theory of Change and share updates with the Northwest CPI Collaborative. | Program Associate II | 2024-02-27 | 2024-03-10 | Complete
7 | Follow up with Arcata House Partnership to learn how they are increasing clients, as some organizations are having difficulty with receiving referrals and large enough case loads to be sustainable. | Program Associate II | 2024-02-27 | 2024-03-10 | Complete
8 | PHIL will develop and distribute a flyer that shares an overview of CPI Facilitators Required Activities, as well as contact information for the programs administrators. This will be distributed as an email to the convenings attendants, and will be shared on the PATH CPI website. | Program Associate II | 2024-01-24 | 2024-01-29 | Complete
9 | PHIL will develop and distribute an "Action Lever Reference Guide" that shares an overview of DHCS Action Levers. This will be distributed as an email to the convenings attendants, and will be shared on the PATH CPI website. | Program Manager | 2024-01-25 | 2024-01-29 | Complete
10 | Develop a Q&A document for questions that were not answered. Once answered, the Q&A document will be sent to participants and will be added to the Readiness Roadmap website. | PHIL | 12/05/2023 | 12/15/2023 | Completed
11 | Ask Open Door Community Health Centers if we can share their CHW workflow. | PHIL | 12/05/2023 | 12/15/2023 | Completed
12 | Coordinate a conversation with PHC to learn how they can deliver updates regarding Birth Equity. | PHIL | 12/05/2023 | 12/15/2023 | Incomplete
13 | Support conversations between local HIE and DHCS to learn more about the “Closed Loop Referral System”. | PHIL | 12/05/2023 | 12/15/2023 | Complete
14 | Learn how HealthBegins is supporting their collaboratives with Case Consulting. | PHIL | 11/01/2023 | 11/15/2023 | Complete
15 | Uplift provider concerns DHCS’ marketing strategies for ECM and CS. | PHIL | 11/01/2023 | 11/15/2023 | Complete
16 | Issue Tracker additions: | PHIL | 8/28/2023 | 9/15/2023 | Completed
17 | - Accessibility to tools from PHC including z codes, g code sheets, and eligible participant lists.
18 | - ECM and/or CS implementation barriers unique to school-based clinics.
19 | Mapping care coordination processes. | PHIL | 6/29/2023 | 8/5/2023 | No longer a priority of the collaborative
20 | Propose monthly meetings with Camden, HC2, HealthBegins and Partnership to efficiently collate common issues among CPI collaboratives across Northern California counties | PHIL | 5/30/2023 | 6/5/2023 | Completed
21 | Strategize methods of collecting the step all participants are at on the Readiness Roadmap (polled during meetings as well as follow-up conversations) | PHIL | 4/21/2023 | 5/5/2023 | Completed
22 | A report of the initial Asset Mapping Survey findings is to be shared with the participants on the website. | MERLIN | 4/21/2023 | 6/5/2023 | Completed
23 | Incorporating charter feedback | PHIL | 1/1/2023 | 3/31/2023 | Completed
24 | PATH CPI Asset Mapping Survey | PHIL | 1/1/2023 | 5/15/2023 | Completed

## Meeting Summary
Key Takeaways & Discussion Themes by Agenda Topic
Topic | Discussion Themes/Key Takeaways | Actions Taken/Next Steps | Best Practices/Lessons Learned
Welcome, Framing, & Check-In | N/A | N/A | N/A
Local Organization Spotlight | Key Takeaways: Although not a local entity, Committee on the Shelterless (COTS), was invited to showcase their organizational strategies and successful implementation of workflows and processes, resulting in achieving a 100% incentive payment for all three QIP (Quality Incentive Program) measures included in Partnership HealthPlan of California's ECM QIP incentive. During their presentation, they delved into their ECM statistics, highlighted key insights gained, demonstrated their data collection and monitoring tools, and offered valuable tips for effective team management and performance enhancement. Currently, only one organization in the Northwest Region, Arcata House Partnership, is scoring 85% - 100% and is earning 100% of their incentive pool. | Next Steps: Coordinate with COTS to collect and share workplans, processes, and templates developed for their QIP program to CPI Participants via the PATH CPI website. | Lesson Learned: PHIL has recognized the importance for organizations to establish a centralized administrative support structure specifically devoted to CalAIM programming. This effort has demonstrated effectiveness in improving data collection, monitoring systems, analytical capabilities, development of tools and workflows, alongside communication strategies. When combined with effective leadership, organizations are making progress in their CalAIM implementation, and like COTS, use these eforts to leverage ECM-related financial incentives, such as the implementation of PHC's QIP.
Utilization Data Informed Goals | Key Takeaways: The MERLIN team disseminated updates gleaned from DHCS's Dashboards representing all seven counties within the Northwest and Southwest regions, highlighting notable trends over time. The presentation featured visuals depicting Enhanced Care Management and Community Supports provider networks alongside enrollment statistics, offering a snapshot of the current CalAIM environment. The key insight derived from the data presentation is that utilization of ECM services needs to increase by over 200% to reach a 1% ECM penetration rate. While the overall trend was positive over the past year, evidenced by both increased provider numbers and capacity, much more work is needed to increase provider capacity in the region. | Next Steps: Continue the core work of the PATH CPI initiative to outreach and support CalAIM contract development, strengthen community-based referral, and monitor access to and utilization of CalAIM services. | Lesson Learned: This presentation stimulated interest and fostered an appreciation for leveraging data to guide discussions and the CPI intiative's AIM statement, notably among the MCP participants present in the room.
Update from Partnership HealthPlan of California | Key Takeaways: PHC extended an invitation to participants to join the ECM and CS roundtables (linked in the "Shared Collaborative Resources" section below). Additionally, a friendly reminder was shared to ensure timely submission of applications for their IPP funding opportunity, with the deadline approaching on the 26th. | N/A | N/A
Spotlight on CalAIM Program and Revenue Enhancement Strategies | Key Takeaways: Partnership HealthPlan of California showcased their ECM QIP program, which offers a maximum of $100 per member per month to organizations successfully executing the three QIP Measures: timely reporting, PHQ-9 Depression Screening, and Blood Pressure Monitoring. Their presentation encompassed the program's evolution, core principles, timelines, and measurement specifics. Additionally, they spotlighted local organizations achieving exceptional scores ranging from 85% to 100%, securing full access to their incentive pool. | Next Steps: Coordinate with Partnership HealthPlan to co-facilitate a training for their QIP program measurements, dependent on the needs of participants. (See Lessons Learned) | Lessons Learned: n=7 i. Which PHP ECM QIP incentives is my organization receiving? 1) Measure 1. (3/7, 43%) 2) Measure 2. (3/7, 43%) 3) Measure 3. (3/7, 43%) 4) I don't know (0/7, 0%) 5) None (2/7, 29%) 6) N/A (2/7, 29%) ii. Respondents selected either "Successfully implementing Partnership HealthPlan's ECM QIP Program. Everything has been running smoothly" (2/3, 66%) or "Implementing Partnership HealthPlan's ECM QIP Program but have a couple of challenges, questions, and/or barriers" (1/3, 33%) iii. If PHIL held an in-person pop-up training on the Depression Screening and Blood Pressure Screening QIPS, would your organization be interested in participating 1) Yes! (3/7, 43%) 2) Unsure (2/7, 29%) 3) Not interested (0/7,0%) 4) N/A (2/7, 29%)
PATH CPI Updates and Upcoming Events | Key Takeaways: PHIL is planning to release its first policy brief in May. | N/A | N/A
Evaluation & Close | N/A | N/A | N/A
Identified Gaps/Challenges in CalAIM/ECM/Community Supports
Topic | Gaps/Challenges Identified | Actions Taken/Next Steps | Best Practices/Lessons Learned
Local ECM Financial Opportunity | The region has only one organization effectively implementing the MCP's ECM QIP, representing a significant missed opportunity to potentially collect an additional $100 per member per month. | Next Steps: PHIL will collaborate with PHC to design an in-person training session aimed at helping organizations overcome barriers. | N/A
Identified Successes Experienced by Participants
Topic | Successes Identified | Actions Taken/Next Steps | Best Practices/Lessons Learned
Peer Learning | Engaging in peer learning opportunities, starting from high-level concepts down to specific processes and templates, proves invaluable for organizations at any stage of CalAIM implementation. | Next Steps: Coordinate with COTS to collect and share workplans, processes, and templates developed for their QIP program to CPI Participants via the PATH CPI website. | N/A
Summary of Complaints & Grievances
Topic | Summary of Complaint/Grievance | Actions Taken | Next Steps
N/A | N/A | N/A | N/A
MCP Engagement (List all MCPs who should be engaged regardless of attendance) |  |  |  | KEY
MCP Name | Current Status of Relationship | MCP Engagement in Collaborative | Engagement Concerns & Notes | Acceptable | MCP attends 50%-75% collaborative convenings, MCP is responsive to collaborative requests but follow up is needed by facilitator
| i.e. Excellent > Acceptable > Needs Improvement > In Direct Contact With > No Contact | Yes/No |  | Excellent | MCP is engaged in collaborative, MCP attends 75%-100% collaborative convenings, MCP is presenter during collaborative meetings, MCP provides feedback and data where applicable, MCP works in partnership with facilitator and collaborative
Partnership HealthPlan of California | Excellent | Yes | PHC provides pertinent updates during each monthly convening. This month, they expanded on their offerings by wecoming a different team member to present their Enhanced Care Management Quality Incentive Program (QIP), an exclusive funding opportunity not available through all MCPs. The representative showcased impressive expertise, confidently addressing all inquiries from the audience. | In Direct Contact With | Facilitator has direct contact with MCP, MCP may not currently be attending collaboratives, MCP may be transitioning in 2024 and not yet active in collaborative
|  |  |  | Needs Improvement | MCP is not or inconsistently engaged in collaborative, MCP attends 0%-25% of collaborative convenings, difficulties consulting with MCP, further partnership and relationship building is required
|  |  |  | No Contact | There is no contact with MCP, MCP is not present for collaborative meetings, no relationship built with MCP
Shared Collaborative Resources
Resource | Category/Type | Link/Access Information
PATH CPI | Website | https://pophealthinnovationlab.org/projects/path/
CalAIM Provider Forum | Registration Link | https://bit.ly/3Q5tdJH
Native Lands | Website | https://native-land.ca
COTS QIP Tracking Template | Spreadsheet | https://pophealthinnovationlab.org/wp-content/uploads/2024/04/Updated-QIP-Tracking-Template.xlsx
COTS Website | Website | https://cots.org/
Executive Summary A Section of the ECM and Community Supports Quarterly Implementation Report | Website | https://storymaps.arcgis.com/collections/a07f998dfefa497fbd7613981e4f6117?item=1
Partnership HealthPlan of California ECM Roundtable | Webinar | https://bit.ly/4cmy8Q2
Partnership HealthPlan of California Community Supports Roundtable | Webinar | https://bit.ly/3vhc34b
Partnership HealthPlan of California's ECM QIP website | Website | https://www.partnershiphp.org/Providers/Quality/Pages/ECM-QIP-Enhanced-Care-Management.aspx
CalAIM budget estimator tool | Website | https://camdenhealth.org/resources/calaim-budget-estimator-tool/
Northwest CPI Collaborative Convenings: | Registration Link | https://bit.ly/4a7MW3G
Northwest CPI Collaborative Office Hours Wednesdays: | Registration Link | https://bit.ly/3TKzMDW
Northwest CPI Collaborative Office Hours Mondays: | Registration Link | https://bit.ly/4a1iGan

## Meeting Attendance
Note: If your office hours were combined with another collaborative or facilitator group, please complete columns D & E.
Organization Name | Participant Name | Email | Collaborative Group | Facilitator Group
Unknown | 14803299322 | 14803299322 | Northwest | Population Health Innovation Lab, Public Health Institute
First 5 Humboldt | Aaron Wythe | Aaron Wythe | Northwest | Population Health Innovation Lab, Public Health Institute
Humboldt County | Aaron Zell | Aaron Zell | Northwest | Population Health Innovation Lab, Public Health Institute
Partnership Health Plan of California | Amy McCune | Amy McCune | Northwest | Population Health Innovation Lab, Public Health Institute
Partnership Health Plan of California | Ashley Peel | Ashley Peel | Northwest | Population Health Innovation Lab, Public Health Institute
Partnership Health Plan of California | Carolyn Moulton | Carolyn Moulton | Northwest | Population Health Innovation Lab, Public Health Institute
NCHIIN | Chris Davis | Chris Davis | Northwest | Population Health Innovation Lab, Public Health Institute
Humboldt County | Cindy Sutcliffe | Cindy Sutcliffe | Northwest | Population Health Innovation Lab, Public Health Institute
Del Norte Mission Possible | Daphne Cortese-Lambert | Daphne Cortese-Lambert | Northwest | Population Health Innovation Lab, Public Health Institute
Arcata House Partnership | Desiray Avila | Desiray Avila | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Esmeralda Salas | Esmeralda Salas | Northwest | Population Health Innovation Lab, Public Health Institute
Partnership Health Plan of California | Jeannine O'Connell | Jeannine O'Connell | Northwest | Population Health Innovation Lab, Public Health Institute
NCHIIN | Jessica Osborne-Stafsnes | Jessica Osborne-Stafsnes | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Jessica Sanchez | Jessica Sanchez | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Kathryn Stewart | Kathryn Stewart | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Katie Christian | Katie Christian | Northwest | Population Health Innovation Lab, Public Health Institute
Community Support Network | Kym Centaro | Kym Centaro | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Megan Kenney | Megan Kenney | Northwest | Population Health Innovation Lab, Public Health Institute
Humboldt County | Morgan Brannon | Morgan Brannon | Northwest | Population Health Innovation Lab, Public Health Institute
Humboldt County | Raul Torres | Raul Torres | Northwest | Population Health Innovation Lab, Public Health Institute
Open Door Community Health Centers | Sandra Miliotti | Sandra Miliotti | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Seun Aluko | Seun Aluko | Northwest | Population Health Innovation Lab, Public Health Institute
COTS | Shannon Garay | Shannon Garay | Northwest | Population Health Innovation Lab, Public Health Institute
St. Joseph Hospital/Redwood Memorial Hospital | Sharon Hunter | Sharon Hunter | Northwest | Population Health Innovation Lab, Public Health Institute
Hartsfield Consulting | Stefani Hartsfield | Stefani Hartsfield | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Sue Grinnell | Sue Grinnell | Northwest | Population Health Innovation Lab, Public Health Institute
Humboldt County | Tami Wandel | Tami Wandel | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Tammy Chandler | Tammy Chandler | Northwest | Population Health Innovation Lab, Public Health Institute
Partnership Health Plan of California | Teresa Tillman | Teresa Tillman | Northwest | Population Health Innovation Lab, Public Health Institute
Partnership Health Plan of California | Vicky Klakken | Vicky Klakken | Northwest | Population Health Innovation Lab, Public Health Institute

## Lists (hidden)
Meeting Type
Monthly Collaborative Convening
Office Hours