## Agenda
| #VALUE! |  | #VALUE!
Collaborative: | Northwest Collaborative Planning & Implementation Group
Meeting Type: | Monthly Collaborative Convening
Date: | Tuesday, May 21, 2024 | Location: | Zoom Link
Time: | 1:00 – 2:00 PM | Facilitator: | Population Health Innovation Lab, Public Health Institute
High Level Agenda
| Topic | Key Questions
Welcome, Framing, & Check-In
| Spotlight on Community Care Hubs | What innovative solutions are available to mitigate CalAIM participation barriers, address administrative challenges, and fully implement CalAIM Enhanced Care Management and Community Supports?
| Local Organization Spotlight | What regional CalAIM innovations are being led by North Coast Health Improvement and Information Network (NCHIIN)?
| Update from Partnership HealthPlan of California | What updates from PHC will impact existing and prospective ECM and Community Supports processes?
| Updates about Upcoming Events | Invitation to an in-person QIP training on 6/10 in McKinleyville, CA with Partnership HealthPlan of California.
Evaluation & Close
New Action Items (Identified this Meeting)
No. | Action Item | Owner | Created | Deadline | Status
1. | Partner with NCHIIN to more broadly share their successful development and pilot of an integrated ECM Module within their Community Information Exchange (CIE), which uses the NinePatch® Whole Person Care SDOH Solution platform. | PHIL | 2024-05-21 | 2024-08-31 | Ongoing
2. | Partner with NCHIIN to support their community discovery work, which will focus on understanding the need for a local/regionalCalAIM administrative hub, and will help determine if a hub can help develop CalAIM providers and services in the region. | PHIL | 2024-05-21 | 2024-11-30 | Ongoing
3. | Host an ECM QIP training with Partnership HealthPlan of California as a "proof of concept" with the NW collaborative. Gather feedback, analyze the effectiveness of the training, and share the outcomes and conclusions with the collaborative and with other PATH CPI facilitators. | PHIL | 2024-05-21 | 2024-07-31 | In progress
Open Action Items
No. | Action Item | Owner | Created | Deadline | Status
1. | Coordinate with Partnership HealthPlan to co-facilitate a training for their QIP program measurements, dependent on the needs of participants. (See Lessons Learned) | Program Manager and Program Associate II | 2024-04-22 | 2024-05-03 | In Progress
2. | Meet with NCHIIN and Humboldt 211, which support local service provider information and referral networks, to explore how they might strengthen knowledge and informaton sharing across local organizations in order to increase CalAIM community-based referrals and service utilization. | Program Manager | 2024-03-25 | 2023-04-30 | In Progress
3. | Integrate the issue of confident and confidential care coordination into future programming. | Program Associate II and Program Manager | 2024-02-27 | 2024-05-01 | Incomplete
4. | Follow up with Action Items identified during the Ecosystems Activity | CPI participants with Program Manager support | 2024-02-27 | 2024-03-15 | Partially complete and in progress
5. | Invite K'ima:w Medical Center as a spotlight organization so they could share more abour their journey to becoming a ECM and Community Supports provider. | Program Associate II | 2024-02-27 | 2024-03-10 | Pending response
6. | Begin program development of the "Administrative Burden" Test of Change. This includes conducting a landscape assessment to learn the general understanding of hub models and glean regional interest. | Program Manager | 2024-01-26 | 2024-04-20 | In Progress
7. | Schedule meeting with NCHIIN and Arcata House to learn about the pilot program. | PHIL | 11/15/2023 | 3/30/2024 | In Progress
Ongoing Action Items
No. | Action Item | Owner | Created | Deadline | Status
1. | Continue the core work of the PATH CPI initiative to outreach and support CalAIM contract development, strengthen community-based referral, and monitor access to and utilization of CalAIM services. | PHIL | 2024-04-22 | Continuous | Ongoing
2. | Monitor referral progress to determine if additional community-based and provider referrals follow increased knowledge/awareness. | Program Manager with support of MERLIN | 2024-03-26 | Continuous | Ongoing
3. | Integrate tools for sustainability through the upcoming convenings, resources and conversations. | PHIL | 8/28/2023 | Continuous | Ongoing
4. | Integrate updated tools and resources in the Pre-Contract and Post-Contract Process, Tools, and Solutions packet. Share updates with collaboratives and CPI Facilitators as they become available. | PHIL | 8/28/2023 | Continuous | Ongoing
5. | Follow up with organizations who show great and minimal progress along the Readiness Roadmap for support and guidance. | PHIL | 6/29/2023 | Continuous | Strategizing
6. | Re-vamp website with developing resource and information needs to continue serving current and prospective CPI participants | PHIL | 5/30/2023 | Continuous | Implementing
7. | Develop collaborative systems improvement strategies. | PHIL | 4/21/2023 | Continuous | Strategizing
8. | Identify specific capacity building training. | PHIL | 4/21/2023 | Continuous | Outlined and finalizing
9. | Network and relationship building with new members added to the asset maps. | PHIL | 4/21/2023 | Continuous | Strategizing
10. | Identify existing coalitions, collaboratives and roundtables for ECM, Community supports | PHIL and CPI Partners | 3/30/2023 | Continuous | Data synthesized by mapping project will help to identify these initiatives.
11. | Recruitment of new CPI participants | PHIL and CPI Partners | 1/1/2023 | Continuous | Implementing
Closed Action Items
No. | Action Item | Owner | Created | Deadline | Status
1. | Coordinate with COTS to collect and share workplans, processes, and templates developed for their QIP program to CPI Participants via the PATH CPI website. | Program Associate II | 2024-04-22 | 2024-04-22 | Pending
2. | Adjust the timing of monthly meetings based on participants' preferences. | Program Associate II | 2024-03-22 | 2023-04-15 | Complete
3. | Evaluate and explore the notion of feasibility, sustainability and braided funding in upcoming Northwest PATH CPI Programming | Program Manager | 2024-02-27 | 2024-05-01 | Completed
4. | Coordinate with Camden Coalition on when to debut the "Go, No Go Feasibility Tool" | Program Associate II | 2024-02-27 | 2024-03-10 | Complete
5. | Several questions emerged about Administrative Hubs/Care Hubs – policy follow up with PHC, PCG/DHCS to inform future CPI participant trainings. | Program Manager | 2024-02-27 | 2024-03-10 | Completed
6. | Follow up with Native Spirit Consulting to learn how PHIL could be of support and service to organizations interestested in participating in CalAIM. | Program Associate II and Program Manager | 2024-02-27 | 2024-03-10 | Completed
7. | Revise the Theory of Change and share updates with the Northwest CPI Collaborative. | Program Associate II | 2024-02-27 | 2024-03-10 | Complete
8. | Follow up with Arcata House Partnership to learn how they are increasing clients, as some organizations are having difficulty with receiving referrals and large enough case loads to be sustainable. | Program Associate II | 2024-02-27 | 2024-03-10 | Complete
9. | PHIL will develop and distribute a flyer that shares an overview of CPI Facilitators Required Activities, as well as contact information for the programs administrators. This will be distributed as an email to the convenings attendants, and will be shared on the PATH CPI website. | Program Associate II | 2024-01-24 | 2024-01-29 | Complete
10. | PHIL will develop and distribute an "Action Lever Reference Guide" that shares an overview of DHCS Action Levers. This will be distributed as an email to the convenings attendants, and will be shared on the PATH CPI website. | Program Manager | 2024-01-25 | 2024-01-29 | Complete
11. | Develop a Q&A document for questions that were not answered. Once answered, the Q&A document will be sent to participants and will be added to the Readiness Roadmap website. | PHIL | 12/05/2023 | 12/15/2023 | Completed
12. | Ask Open Door Community Health Centers if we can share their CHW workflow. | PHIL | 12/05/2023 | 12/15/2023 | Completed
13. | Coordinate a conversation with PHC to learn how they can deliver updates regarding Birth Equity. | PHIL | 12/05/2023 | 12/15/2023 | Incomplete
14. | Support conversations between local HIE and DHCS to learn more about the “Closed Loop Referral System”. | PHIL | 12/05/2023 | 12/15/2023 | Complete
15. | Learn how HealthBegins is supporting their collaboratives with Case Consulting. | PHIL | 11/01/2023 | 11/15/2023 | Complete
16. | Uplift provider concerns DHCS’ marketing strategies for ECM and CS. | PHIL | 11/01/2023 | 11/15/2023 | Complete
17. | Issue Tracker additions: - Accessibility to tools from PHC including z codes, g code sheets, and eligible participant lists. - ECM and/or CS implementation barriers unique to school-based clinics. | PHIL | 8/28/2023 | 9/15/2023 | Completed
18. | Mapping care coordination processes. | PHIL | 6/29/2023 | 8/5/2023 | No longer a priority of the collaborative
19. | Propose monthly meetings with Camden, HC2, HealthBegins and Partnership to efficiently collate common issues among CPI collaboratives across Northern California counties | PHIL | 5/30/2023 | 6/5/2023 | Completed
20. | Strategize methods of collecting the step all participants are at on the Readiness Roadmap (polled during meetings as well as follow-up conversations) | PHIL | 4/21/2023 | 5/5/2023 | Completed
21. | A report of the initial Asset Mapping Survey findings is to be shared with the participants on the website. | MERLIN | 4/21/2023 | 6/5/2023 | Completed
22. | Incorporating charter feedback | PHIL | 1/1/2023 | 3/31/2023 | Completed
23. | PATH CPI Asset Mapping Survey | PHIL | 1/1/2023 | 5/15/2023 | Completed

## Meeting Summary
Key Takeaways & Discussion Themes by Agenda Topic
Topic | Discussion Themes/Key Takeaways | Actions Taken/Next Steps | Best Practices/Lessons Learned
Welcome, Framing, & Check-In | Discussion Themes: PHIL offered the following check-in question for attendees: "when you hear the term "hub" what does it mean to you? What would it do? Key Takeaways: Similar to the Southwest meeting (SW), attendees from the Northwest Collaborative (NW) expressed varied understanding of a hub model and how it functions. A common theme that emerged from the responses was an understanding that a hub should serve as a "meeting place" for multiple agencies. | N/A | Lessons Learned: The term "hub" has many interpretations and functions that differ between sectors. The group demonstrated a shared understanding that a hub should be a "meeting place" for multiple organizations.
Spotlight on Community Care Hubs | Discussion Themes: The purpose of this presentation was to present background information on the emergence of hub models implemented in the context of CalAIM. PHIL provided an overview of federal investment in community care hubs, starting in 2012 until today. PHIL additionally presented multiple examples of hub models from across California to bring clarity to the concept for attendees. The Community Care Hub Model outlined in the November 2023 HHS Strategic Approach to Addressing Social Determinants of Health to Advance Health Equity report was also shared. Key Takeaways: There exist multiple examples of emerging hubs being utilized for CalAIM. These include the Aliados Health Administrative Services Entity, Alameda County's Care Neighborhood, and Kaiser Permanente's three network lead entities (Full Circle Health Network, Independent Living Systems, and Partners in Care Foundation). Community care hubs serve as a promising model to coordinate health & social care, address social determinants of health, and advance health equity. | N/A | Lessons Learned: There are several emerging CalAIM hub models across the state of California that hold promise for facilitating safe and seamless coordination among CalAIM service providers. PHIL will continue to monitor and learn from these models for sharing back to the NW collaborative.
Local Organization Spotlight | Discussion Themes: The North Coast Health Improvement and Information Network (NCHIIN) coordinates the health information exchange (HIE) and community information exchange (CIE) of Humboldt County. Jessica Osborne-Stafsnes, NCHIIN's COO, presented background information on how the CIE was established and their recent efforts to leverage the robust infrastructure of the CIE for the purposes of CalAIM. Key Takeaways: Jessica presented an excellent example of how existing information sharing networks can be leveraged to implement a hub for the purposes of CalAIM. Most notably, Jessica discussed NCHIIN's partnership with Arcata House (a large ECM provider in the area) to develop a specific ECM module within their CIE. The module has interoperability with Arcata House's EHR Point Click Care and has allowed providers to see up-to-date information on a clients care plan. A representative from Arcata House shared how beneficial the module has been and how this translates to improved care for clients. Humboldt County's Accountable Community for Health (ACH), the Humboldt Community Health Trust, will be leading community discovery work to identify the infrastructure and resource needs to bolster the CIE for CalAIM use. | Action Items: 1. Partnership Health Plan applauded the work of NCHIIN and recommended that they share this example with other PATH collaboratives as well as DHCS. It was recommended that the community benefitting from NCHIIN's work should advocate for this model to be accepted and duplicated across the state. 2. PHIL is partnering with NCHIIN to conduct their community discovery work focused on understanding the need for a CalAIM administrative hub in the region. PHIL also hopes to use this as an opportunity recruit new CalAIM providers in the region. | Best Practices: NCHIIN's efforts to build on the existing infrastructure of a trusted source of information, their CIE, demonstrate best practices for establishing a hub model for the purposes of CalAIM. Communities with similar existing infrastructure and resources should leverage this rather than starting something completely new.
Update from Partnership HealthPlan of California | Discussion Themes: Partnership Health Plan shared that they recently switched the format of their ECM attestation form from a PDF to a survey. They also encouraged participants to join their ECM Roundtable Meeting on 5/16/24 and CS Roundtable Meeting on 5/30/24. Key Takeaways: ECM providers should be sure to use the updated attestation survey instead of the PDF form. | N/A | N/A
Updates about Upcoming Events | Discussion Themes: PHIL shared that they will be holding a first of its kind, in-person ECM QIP Training in collaboration with Partnership Health Plan on June 10, 2024 at the Holiday Inn Express in McKinleyville, CA. The event will provide training on blood pressure monitoring and depression screening, as well as timely reporting tips. PHIL and Partnership Health Plan are excited to pilot this event and hopefully provide more in the future. PHIL also plans to release their PATH CPI Policy Brief by June 1, 2024. The brief will include information from the May revise. Key Takeaways: PATH participants are encouraged to sign-up for the ECM QIP Training on June 10, 2024. | Action Items: PHIL is hosting the first ever in-person ECM QIP training with Partnership HealthPlan of California in the NW Region, which will serve as a "proof of concept" and inform a second training that is planned in the SW Region in August. PHIL is planning to gather feedback and analyze the effectiveness of the training. PHIL will share the outcomes and conclusions with the collaborative and with other PATH facilitators. | N/A
Evaluation & Close | N/A | N/A | N/A
Identified Gaps/Challenges in CalAIM/ECM/Community Supports
Topic | Gaps/Challenges Identified | Actions Taken/Next Steps | Best Practices/Lessons Learned
Provider Shortage | PHIL has identified a need for more local providers to serve the large population of eligible members in the NW region, as indicated by the low penetration rate that was shared last month. | PHIL is partnering with NCHIIN in their community discovery efforts to understand the local/regional needs for a CalAIM administrative hub as well as recruit new users and CalAIM providers. | PHIL is leveraging existing efforts to better connect with organizations in the community to encourage adoption and implementation of CalAIM services.
Identified Successes Experienced by Participants
Topic | Successes Identified | Actions Taken/Next Steps | Best Practices/Lessons Learned
NCHIIN & Arcata House Partnership | NCHIIN partnered with Arcata House (a large ECM provider in the area) to develop a specific ECM module within their CIE. The module has interoperability with Arcata House's EHR Point Click Care and has allowed providers to see up-to-date information on a clients care plan. | N/A | The partnership between the CIE entity (NCHIIN) and service provider organization (Arcata House) proved successful in developing an effective module with interoperability with EHR platforms. The module is tailored to the needs of Arcata House and has allowed for improved patient care. It has also received support and encouragement from the local MCP.
Community Discovery Efforts | Humboldt County's Accountable Community for Health (ACH), the Humboldt Community Health Trust, will be leading community discovery work to identify the infrastructure and resource needs to bolster the CIE for CalAIM use. | N/A | Collaboration with other county-wide initiatives, such as the Humboldt County ACH, will allow for pooling of resources and capacity to achieve common goals in improving community health. It is important for CalAIM initiatives to be infused into existing efforts.
Summary of Complaints & Grievances
Topic | Summary of Complaint/Grievance | Actions Taken | Next Steps
N/A | N/A | N/A | N/A
MCP Engagement (List all MCPs who should be engaged regardless of attendance) |  |  |  | KEY
MCP Name | Current Status of Relationship | MCP Engagement in Collaborative | Engagement Concerns & Notes | Acceptable | MCP attends 50%-75% collaborative convenings, MCP is responsive to collaborative requests but follow up is needed by facilitator
| i.e. Excellent > Acceptable > Needs Improvement > In Direct Contact With > No Contact | Yes/No |  | Excellent | MCP is engaged in collaborative, MCP attends 75%-100% collaborative convenings, MCP is presenter during collaborative meetings, MCP provides feedback and data where applicable, MCP works in partnership with facilitator and collaborative
Partnership HealthPlan of California | Excellent | Yes | PHC provides pertinent updates during each monthly convening and actively participates in topical discussions during each convening. PHC will be supporting an In-Person Enhanced Care Management Quality Incentive Program (QIP) training, hosted by PHIL, in McKinleyville on June 10th and in Santa Rosa on August 22nd. | In Direct Contact With | Facilitator has direct contact with MCP, MCP may not currently be attending collaboratives, MCP may be transitioning in 2024 and not yet active in collaborative
|  |  |  | Needs Improvement | MCP is not or inconsistently engaged in collaborative, MCP attends 0%-25% of collaborative convenings, difficulties consulting with MCP, further partnership and relationship building is required
|  |  |  | No Contact | There is no contact with MCP, MCP is not present for collaborative meetings, no relationship built with MCP
Shared Collaborative Resources
Resource | Category/Type | Link/Access Information
PATH CPI | Website | https://pophealthinnovationlab.org/projects/path/
Native Lands | Website | https://native-land.ca
Partnership to Align Social Care Website | Website | Community Care Hubs ¦ Partnership to Align Social Care (partnership2asc.org)
Community Care Hubs: A Promising Model for Health and Social Care Coordination | Report | https://aspe.hhs.gov/sites/default/files/documents/5b8cba1351a99e904589f67648c5832f/health-social-care-coordination.pdf
NCHIIN Website | Website | https://www.nchiin.org/
Partnership HealthPlan of California ECM Roundtable | Webinar | https://bit.ly/4cmy8Q2
Partnership HealthPlan of California Community Supports Roundtable | Webinar | https://bit.ly/3vhc34b
ECM QIP Pop-up Event Registration | Registration Link | https://www.eventbrite.com/e/calaim-ecm-quality-incentive-program-qip-in-person-tickets-909972180287?aff=oddtdtcreator

## Meeting Attendance
Note: If your office hours were combined with another collaborative or facilitator group, please complete columns D & E.
Organization Name | Participant Name | Email | Collaborative Group | Facilitator Group
Humboldt County | Aaron Zell | azell@co.humboldt.ca.us | Northwest | Population Health Innovation Lab, Public Health Institute
Partnership Health Plan of California | Ashley Peel | apeel@partnershiphp.org | Northwest | Population Health Innovation Lab, Public Health Institute
Moms Meals | Brianna Moncada | brianna.moncada@momsmeals.com | Northwest | Population Health Innovation Lab, Public Health Institute
NCHIIN | Chris Davis | cdavis@humboldtipa.com | Northwest | Population Health Innovation Lab, Public Health Institute
Partnership Health Plan of California | Jeannine O'connell | JOConnell@partnershiphp.org | Northwest | Population Health Innovation Lab, Public Health Institute
SacValley MedShare | Jennifer Inden | jennifer.inden@sacvalleyms.org | Northwest | Population Health Innovation Lab, Public Health Institute
NCHIIN | Jessica Osborne-Stafsnes | josborne@nchiin.org | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Kathryn Stewart | kastewart@phi.org | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Katie Christian | kchristian@phi.org | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Megan Kenney | mkenney@phi.org | Northwest | Population Health Innovation Lab, Public Health Institute
Friends Outside | Michael Sorensen | msorensen@friendsoutside.org | Northwest | Population Health Innovation Lab, Public Health Institute
Redwood Rural Health Center | Michele Hernandez | mhernandez@rrhc.org | Northwest | Population Health Innovation Lab, Public Health Institute
Humboldt County | Morgan Brannon | mbrannon@co.humboldt.ca.us | Northwest | Population Health Innovation Lab, Public Health Institute
Humboldt Senior Resource Center | Rachel Sovereign | rsovereign@humsenior.org | Northwest | Population Health Innovation Lab, Public Health Institute
Humboldt County | Raul Torres | rtorres@co.humboldt.ca.us | Northwest | Population Health Innovation Lab, Public Health Institute
Open Door Community Health Centers | Sandra Milliotti | smiliotti@opendoorhealth.com | Northwest | Population Health Innovation Lab, Public Health Institute
Sonoma Connect ¦ Sonoma Unidos | Saskia Garcia | sgarcia@sonomaconnect.org | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Tammy Chandler | tchandler@phi.org | Northwest | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Vicky Klakken | vklakken@partnershiphp.org | Northwest | Population Health Innovation Lab, Public Health Institute
Arcata House Partnership | Virginia Beckman | vbeckman@arcatahouse.org | Northwest | Population Health Innovation Lab, Public Health Institute
Native Spirit Consulting | Zachary Ray | zray@nativespiritconsulting.com | Northwest | Population Health Innovation Lab, Public Health Institute

## Lists (hidden)
Meeting Type
Monthly Collaborative Convening
Office Hours