## Agenda
| #VALUE! |  | #VALUE!
Collaborative: | Southwest Collaborative Planning & Implementation Group
Meeting Type: | Monthly Collaborative Convening
Date: | Wednesday, May 15, 2024 | Location: | Zoom Link
Time: | 12:30 - 2:00 PM | Facilitator: | Population Health Innovation Lab, Public Health Institute
High Level Agenda
| Topic | Key Questions
Welcome, Framing, & Check-In
| Spotlight on Community Care Hubs and Aliados Health’s Administrative Services Entity | What innovative solutions are available to mitigate CalAIM participation barriers, address administrative challenges, and fully implement CalAIM Enhanced Care Management and Community Supports?
| Local Organization Spotlight: Community Action Marin | What lessons can be learned from the experiences of local organizations that have successfully implemented CalAIM with the support of an Administrative Hub?
| Update from Partnership HealthPlan of California | What updates from PHC will impact existing and prospective ECM and Community Supports processes?
Evaluation & Close
| Update from and Extended Time with Kaiser Permanente | What updates from Kaiser Permanente will impact existing and prospective ECM and Community Supports processes? Participants from Marin County, Napa County, and Sonoma County are strongly encouraged to connect with Kaiser Permanente during this extended period to access additional support and educational resources as they navigate through this transitional phase.
New Action Items (Identified this Meeting)
No. | Action Item | Owner | Created | Deadline | Status
1. | Seek clarification on concerns raised regarding a standardized referral form and potential administrative burden for providers only working with one MCP. | Program Manager and Program Support Staff | 2024-05-15 | 2024-07-01 | In Progress
2. | Maintain communication and collaborative with Aliados Health and Partnership Health Plan of California to identify best practices for implementing a hub model and share with CPI participants. | Program Manager and Program Support Staff | 2024-05-15 | Continuous | In Progress
3.
Open Action Items
No. | Action Item | Owner | Created | Deadline | Status
1. | Coordinate with Partnership Health Plan to co-facilitate a training for their QIP program measurements, dependent on the needs of participants. | Program Manager and Program Associate II | 2024-04-22 | 2024-05-03 | In Progress: Training scheduled for August 22, 2024
2. | Gather more information about existing data sources and how DHCS can help support more understanding about the children who qualify for CalAIM ECM and Community Supports. | Program Manager and Program Associate II | 2024-04-22 | 2024-05-15 | Question posed to PCG on 5/7 and in written responses on 5/16 for DHCS in person meeting in June
3. | Gather more information about Sonoma County's Child Welfare Partnership Action Team and how CalAIM services are being developed as part of that work. | Program Manager and Program Associate II | 2024-04-22 | 2024-05-31 | Incomplete
4. | Reach out to Aliados Health for further details on the training services they provide and how that relates to their administrative hub pilot. | Program Manager | 2024-03-22 | 2024-04-22 | Complete
5. | Follow up with Action Items identified during the Ecosystems Activity | CPI participants with Program Manager support | 2024-02-27 | 2024-03-15 | In Progress
6. | Facilitate and support conversations with local MTM entity and DHCS. | PHIL | 12/05/2023 | 12/30/2024 | Incomplete
7. | PHIL will connect with Turning Point to design workflows on case consultation efforts. | PHIL | 11/01/2023 | 11/15/2023 | Incomplete
8. | PHIL will connect with Child Parent Institute and Santa Rosa Community Health Centers to learn more about their ECM implementation improvements. | PHIL | 11/01/2023 | 11/15/2023 | Complete
Ongoing Action Items
No. | Action Item | Owner | Created | Deadline | Status
1. | Evaluate and explore the notion of feasibility, sustainability and braided funding in upcoming Southwest PATH CPI Programming | Program Manager | 2024-02-27 | 2024-05-01 | Continuous
2. | Facilitate and support conversations between ECM, Community Supports providers and regional MCPs. | PHIL | 12/05/2023 | Continuous | Continuous
3. | Identify strategies to address gaps in outreach and recruitment strategies. | PHIL | 11/01/2023 | Continuous | Continuous
4. | Continue populating a system for collecting, collating, collaborating, and sharing workarounds to issues identified in the collaborative. | PHIL | 6/14/2023 | Continuous | Continuous
5. | Integrate tools for sustainability through the upcoming convenings, resources and conversations. | PHIL | 8/28/2023 | Continuous | Continuous
6. | Integrate updated tools and resources in the Pre-Contract and Post-Contract Process, Tools, and Solutions packet. Share updates with collaboratives and CPI Facilitators as they become available. | PHIL | 8/28/2023 | Continuous | Continuous
7. | Follow up with organizations who show great and minimal progress along the Readiness Roadmap for support and guidance. | PHIL | 6/29/2023 | Continuous | Continuous
8. | Re-vamp website with developing resource and information needs to continue serving current and prospective CPI participants | PHIL | 5/30/2023 | Continuous | Continuous
9. | Develop collaborative systems improvement strategies. | PHIL | 4/21/2023 | Continuous | Strategizing
10. | Identify specific capacity building training. | PHIL | 4/21/2023 | Continuous | Outlined and finalizing
11. | Network and relationship building with new members added to the asset maps. | PHIL | 4/21/2023 | Continuous | Strategizing
12. | Identify existing coalitions, collaboratives and roundtables for ECM, Community supports | PHIL and CPI Partners | 3/30/2023 | Continuous | Data synthesized by mapping project will help to identify these initiatives.
13. | Recruitment of new CPI participants | PHIL and CPI Partners | 1/1/2023 | Continuous | Implementing
Closed Action Items
No. | Action Item | Owner | Created | Deadline | Status
1. | Coordinate with COTS to collect and share workplans, processes, and templates CPI Participants on the PATH CPI website. | Program Associate II | 2024-04-22 | 2024-04-22 | Complete
2. | Invite Aliados Health to present at a future meeting and share more details about their model, services and successes of their administrative hub pilot. | Program Manager | 2024-03-22 | 2024-04-22 | Complete
3. | Follow up with the Local Mendocino CalAIM Collaborative to learn how PHIL could support their collaboration with the local Accountable Communities for Health (Healthy Mendocino). | Program Manager | 2024-03-22 | 2024-04-22 | Complete
4. | Invite Kaiser Permanente to present in more detail their "No-Wrong-Door" referral and authorization processes and facilitate learning about how it differs from PHC's processes. | Program Manager | 2024-03-22 | 2024-04-22 | Complete
5. | Adjust the timing of monthly meetings based on participants' preferences. | Program Associate II | 2024-03-22 | 2024-04-15 | Complete
6. | Clarify timelines and processes for accessing Kaiser Permanente IPP funds. | Program Manager | 2024-03-22 | 2024-04-22 | Complete
7. | Several questions emerged about Administrative Hubs/Care Hubs – policy follow up with PHC, PCG/DHCS to inform future CPI participant trainings. | Program Manager | 2024-02-27 | 2024-03-10 | Complete
8. | Coordinate with Camden Coalition on when to debut the "Go, No Go Feasibility Tool" | Program Associate II | 2024-02-27 | 2024-03-10 | Complete
9. | Revise the Theory of Change and share updates with the Southwest CPI Collaborative. | Program Associate II | 2024-02-27 | 2024-03-10 | Complete
10. | Learn how HealthBegins is supporting their collaboratives with Case Consulting. | PHIL | 11/01/2023 | 11/15/2023 | Complete
11. | Uplift provider concerns DHCS’ marketing strategies for ECM and CS. | PHIL | 11/01/2023 | 11/15/2023 | Complete
12. | Request a meeting with CSN to submit a “Success Story” form for the Department of Health Care Services. | PHIL | 12/05/2023 | 12/30/2024 | Complete
13. | Develop a Q&A document for questions that were not answered. Once answered, the Q&A document will be sent to participants and will be added to the Readiness Roadmap website. | PHIL | 12/05/2023 | 12/30/2024 | Complete
14. | Set a date for Kaiser to share updates with local ECM and CS providers. | PHIL | 11/01/2023 | 11/15/2023 | Complete
15. | Coordinate a conversation with PHC to learn how they can deliver updates regarding Birth Equity. | PHIL | 12/05/2023 | 12/15/2023 | Complete
14. | Issue Tracker additions: - Accessibility to tools from PHC including z codes, g code sheets, and eligible participant lists. - ECM and/or CS implementation barriers unique to school-based clinics. | PHIL | 8/28/2023 | 9/15/2023 | Completed
15. | Mapping care coordination processes. | PHIL | 6/29/2023 | 8/5/2023 | No longer a priority of the collaborative
16. | Propose monthly meetings with Camden, HC2, HealthBegins and Partnership to efficiently collate common issues among CPI collaboratives across Northern California counties. | PHIL | 5/30/2023 | 6/5/2023 | Completed
17. | Strategize methods of collecting the step all participants are at on the Readiness Roadmap (polled during meetings as well as follow-up conversations) | PHIL | 4/21/2023 | 5/5/2023 | Completed
18. | A report of the initial Asset Mapping Survey findings is to be shared with the participants on the website. | MERLIN | 4/21/2023 | 6/5/2023 | Completed
19. | Incorporating charter feedback | PHIL | 1/1/2023 | 3/31/2023 | Completed
20. | PATH CPI Asset Mapping Survey | PHIL | 1/1/2023 | 5/15/2023 | Completed

## Meeting Summary
Key Takeaways & Discussion Themes by Agenda Topic
Topic | Discussion Themes/Key Takeaways | Actions Taken/Next Steps | Best Practices/Lessons Learned
Welcome, Framing, & Check-In | Discussion Themes: PHIL offered the following check-in question for attendees: "when you hear the term "hub" what does it mean to you? What would it do? Key Takeaways: Attendees demonstrated a variety of perspectives regarding the definition of a hub model and how it functions. |  | Lessons Learned: The term "hub" has many interpretations and functions that differ between sectors.
Spotlight on Community Care Hubs and Aliados Health’s Administrative Services Entity | Discussion Themes: The purpose of this presentation was to present background information on the emergence of hub models implemented in the context of CalAIM. Community care hubs serve as a promising model to coordinate health & social care, address social determinants of health, and advance health equity. PHIL provided an overview of federal investment in community care hubs, starting in 2012 until today. The Community Care Hub Model outlined in the November 2023 HHS Strategic Approach to Addressing Social Determinants of Health to Advance Health Equity report was also shared. Key Takeaways: Aliados Health (Aliados) is a network of community health centers serving Contra Costa, Napa, Marin, Solano, Sonoma, & Yolo counties. The Aliados Administrative Services Entity (ASE) model has been active in the region for one year and is the only hub currently approved by Partnership HealthPlan of California (PHC)). The ASE supports ten organizations thus far, seven CBOs and three clinics, with a desire to expand in the future. The model has proven effective for partners in the region. Despite this excellent example of PHC supporting a Hub Model, there is still confusion over what a hub model is and whether or not it is supported by Managed Care Plans. | Actions Taken: In response to the confusion over whether or not hub models are supported by MCPs, PHC's Regional Director provided clarification on PHC's willingness to support hubs. However, in the absence of a concrete definition of a hub from the state, PHC is trying to best identify what this means and opportunities to best implement hubs in their service areas. PHC's Regional Director indicated a willingness to work with any organizations or networks that are interested in standing up a hub model. Next Steps: Maintain communication and collaborative with Aliados Health and PHC to identify best practices for implementing a hub model and share with CPI participants. | Best Practices: CPI participants present who had previously participated in the PRACTICE initiative (a grant offered by ACEs Aware to support sustainability of ACE screening and response via new CalAIM programs) indicated that some PRACTICE grantees had established successful hub models for ACEs that could be adapted or learned from to address CalAIM hub needs.
Local Organization Spotlight | Discussion Themes: Community Action Marin (CAM) is a local CBO serving Marin County residents. CAM's mission is to make it possible for people in Marin to achieve well-being by providing the vital services they need. Last year, CAM executed a contract with PHC to provide Medi-Cal services; more specifically, a CS program focused on housing. CAM had previously relied on grant funding to support their programs. Upon launch of services, CAM started receiving a high volume of denials and was struggling to keep up with case notes. CAM then pivoted and joined the Aliados Health ASE to streamline the delivery of CS services. Key Takeaways: The team reported improved outcomes after partnering with the Aliados ASE, including decreased denials and increased revenue. In May 2024, CAM reach their caseload capacity for CS housing services. |  | Best Practices: The Aliados ASE has successfully allowed partner ECM/CS providers and CHW providers to focus on direct client care while supplying PHC with the specific reporting, medical billing, and QIP data required from plan members.
Update from Partnership HealthPlan of California | Key Takeaways: Partnership is working with DHCS on the new standardized referral form and will share more information when available. Upcoming meetings include: ECM Roundtable Meeting on 5/16/24 and CS Roundtable Meeting on 5/30/24. Partnership also shared that they are in the process of reviewing IPP grants. They ate expected to announce approvals by 5/28/24. | N/A | N/A
Evaluation & Close | N/A | N/A | N/A
Update from and Extended Time with Kaiser Permanente | Key Takeaways: Kaiser Permanente (KP) shared updated membership numbers in Napa, Marin, and Sonoma counties. KP expects to serve approximately 38,800 members in Napa, Marin, and Sonoma Counties by the end of 2024. KP is offering a free Complex Care certificate for KP's California-based community partners. The training is hosted by the Camden Coalition and covers essential knowledge, skills, and attitudes required to provide complex care. | N/A | N/A
Identified Gaps/Challenges in CalAIM/ECM/Community Supports
Topic | Gaps/Challenges Identified | Actions Taken/Next Steps | Best Practices/Lessons Learned
Hub Model | DHCS has not identified a standardized definition of a care hub, therefore MCPs like Partnership must discern effective models in the region. |  | PHC is interested in better understanding what hubs or networks currently exists in the region.
ECM/CS Provider Information | CPI participants are requesting additional clarity on ECM/CS provider capacity and service region to make informed community-based referrals within the KP network. |  | KP is working on gathering the appropriate information and making it available to community partners.
Telehealth | CPI participants are reporting difficulty discerning whether or not service providers offer brick-and-mortar services or solely telehealth services. For example, some organizations are based in other parts of the state or country but offer telehealth services in the SW region; it is difficult to identify these situations. | N/A | N/A
Referral Process | CPI participants reported concerns over a standardized ECM referral form. A new form may cause unnecessary administrative burden for small organizations currently utilizing the treatment authorization request (TAR) process. | PHIL will seek clarification on concerns raised regarding a standardized referral form and potential administrative burden for providers only working with one MCP. | N/A
Identified Successes Experienced by Participants
Topic | Successes Identified | Actions Taken/Next Steps | Best Practices/Lessons Learned
Hub Model | The Aliados ASE model has successfully supported ten local providers in offering ECM and CS services, increasing enrollment in the community. These organizations likely wouldn't have otherwise had the infrastructure or resources to leverage CalAIM services if not for the ASE model. | Aliados will continue to share lessons learned and best practices related to the ASE model. | Aliados Health's ASE is an example of a promising model as described in the November 2023 HHS report on Community Care Hubs as a strategic approach to address social determinants of health through supporting CalAIM implementation at the local level.
Summary of Complaints & Grievances
Topic | Summary of Complaint/Grievance | Actions Taken | Next Steps
N/A | N/A | N/A | N/A
MCP Engagement (List all MCPs who should be engaged regardless of attendance) |  |  |  | KEY
MCP Name | Current Status of Relationship | MCP Engagement in Collaborative | Engagement Concerns & Notes | Acceptable | MCP attends 50%-75% collaborative convenings, MCP is responsive to collaborative requests but follow up is needed by facilitator
| i.e. Excellent > Acceptable > Needs Improvement > In Direct Contact With > No Contact | Yes/No |  | Excellent | MCP is engaged in collaborative, MCP attends 75%-100% collaborative convenings, MCP is presenter during collaborative meetings, MCP provides feedback and data where applicable, MCP works in partnership with facilitator and collaborative
Partnership HealthPlan of California | Excellent | Yes | PHC provides pertinent updates during each monthly convening and actively participates in topical discussions during each convening. PHC will be supporting an In-Person Enhanced Care Management Quality Incentive Program (QIP) training, hosted by PHIL, in McKinleyville on June 10th and in Santa Rosa on August 22nd. | In Direct Contact With | Facilitator has direct contact with MCP, MCP may not currently be attending collaboratives, MCP may be transitioning in 2024 and not yet active in collaborative
Kaiser Permanente | Excellent | Yes | This month the last 30 minutes of the convening were dedicated to an education and Q&A sessions with Kaiser Permanente, fostering trust-building opportunities and addressing barriers to contracting and CalAIM implementation in Napa, Marin, and Sonoma County. KP has also offered to hold additional Q&A sessions as needed to ensure participant questions and challenges were heard and addressed. | Needs Improvement | MCP is not or inconsistently engaged in collaborative, MCP attends 0%-25% of collaborative convenings, difficulties consulting with MCP, further partnership and relationship building is required
|  |  |  | No Contact | There is no contact with MCP, MCP is not present for collaborative meetings, no relationship built with MCP
Shared Collaborative Resources
Resource | Category/Type | Link/Access Information
PATH CPI | Website | https://pophealthinnovationlab.org/projects/path/
Native Lands | Website | https://native-land.ca
Partnership to Align Social Care Website | Website | Community Care Hubs ¦ Partnership to Align Social Care (partnership2asc.org)
Community Care Hubs: A Promising Model for Health and Social Care Coordination | Report | https://aspe.hhs.gov/sites/default/files/documents/5b8cba1351a99e904589f67648c5832f/health-social-care-coordination.pdf
Aliados Health Website | Website | https://aliadoshealth.org/about-us/
Community Action Marin Website | Website | https://camarin.org/
Partnership HealthPlan of California ECM Roundtable | Webinar | https://bit.ly/4cmy8Q2
Partnership HealthPlan of California Community Supports Roundtable | Webinar | https://bit.ly/3vhc34b
PHIL PATH CPI Website | Website | https://pophealthinnovationlab.org/projects/path/
Southwest CPI Collaborative Convenings: | Registration Link | https://pophealthinnovationlab-org.zoom.us/meeting/register/tZIoduqqpzgoHNMry_n3cy1jvY3wB6Ml-EDG#/registration
Southwest CPI Collaborative Office Hours Wednesdays: | Registration Link | https://bit.ly/3TKzMDW
Southwest CPI Collaborative Office Hours Mondays: | Registration Link | https://bit.ly/4a1iGan

## Meeting Attendance
Note: If your office hours were combined with another collaborative or facilitator group, please complete columns D & E.
Organization Name | Participant Name | Email | Collaborative Group | Facilitator Group
Aliados Health | Amy Anderson | aanderson@aliadoshealth.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Kaiser Permanente | Andrew Tsang | andrew.x.tsang@kp.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Partnership HealthPlan of California | Ashley Peel | apeel@partnershiphp.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Santa Rosa Community Health Centers | Ben Leroi | benl@srhealth.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Partnership HealthPlan of California | Bianca Veneracion | bveneracion@partnershiphp.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Turning Point Community Programs | Casey Arnstrong | caseyogelvie-armstrong@tpcp.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Marin Community Clinic | Cayenne Bierman | cbierman@marinclinic.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Anchor Health Management | Christina Palomo | palomoc@anchorhm.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
West Coast Health | Daniella Donaldson | ddonaldson@wchealth.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Napa County Department of Corrections, Napa County Juvenile Hall | Danielle Richard | dmrichard@wellpath.us | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Community Action Marin | Erin Hawkins | ehawkins@camarin.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Esmeralda | esalas@phi.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Serene Health | Grace Torres | grace@serenehealth.com | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Mendocino County | Heather Criss | crissh@mendocinocounty.gov | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Partnership HealthPlan of California | Jeannine O'Connell | joconnell@partnershiphp.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Marin Center for Independent Living | Joanne Halliday | joanne@marincil.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Sutter Health | Jodi Nerell | jodi.nerell@sutterhealth.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Cere's Project | Karin Pimentel | kpimentel@ceresproject.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Kathryn Stewart | kathryn.stewart@phi.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Katie Christian | kchristian@phi.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
MedZed | Katrina Hopkins | katrina.hopkins@mymedzed.com | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Kerry Landry Health Care Consulting, LLC | Kerry Landry | kerry@klhcc.com | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Community Supports Network | Kym Centaro | kym@csn-mh.com | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
BluePath Health | Lauren Jacobson | lauren.jacobson@bluepathhealth.com | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Marin Probation | Lisa Miller | lmiller@marinschools.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Partnership HealthPlan of California | Lisa OConnell | loconnell@partnershiphp.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Marin Health and Human Services | Lisa Santora | lisa.santora@marincounty.gov | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Partnership HealthPlan of California | Lynn Scuri | lscuri@partnershiphp.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
North Coast Opportunities | Mary Anne Cox | mcox@ncoinc.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Megan Kenney | mkenney@phi.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Mendocino County | Megan Van Sant | vansantm@mendocinocounty.gov | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Marin Center for Independent Living | Nancy Geisse | nancy@marincil.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
J&M Homecare Services, LLC | Natalie Sousa | nsousa@jmhomecare.com | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Providence Adult Day Health Napa Valley | Nora Reilly | nora.reilly@providence.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
BluePath Health | Sarah Kang | sarah.kang@bluepathhealth.com | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Seun Aluko | saluko@phi.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Committee on the Shelterless | Shannon Garay | sgaray@cots.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Private Consultant | Shari Brenner | sbrennerconsulting@sonic.net | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Community Supports Network | Shira Singerman | shira@csn-mh.com | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Sonoma Connect ¦ Sonoma Unidos | Sofia Tecpoyotl | stecpoyotl@sonomaconnect.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Stefani Hartsfield | stefani@hartsfieldhealth.com | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Sue Grinnell | sgrinnell@phi.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Population Health Innovation Lab | Tammy Chandler | tchandler@phi.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Canal Alliance | Tammy Whiteduck | tammyw@canalalliance.org | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Committee on the Shelterless | Teresa Tillman | teresat319@gmail.com | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Roots Food Group | Troy Thomas | troy@rfoodx.com | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute
Native Spirit Consulting | Zachary Ray | zray@nativespiritconsulting.com | Southwest Collaborative | Population Health Innovation Lab, Public Health Institute

## Lists (hidden)
Meeting Type
Monthly Collaborative Convening
Office Hours