## Agenda
| #VALUE! |  | #VALUE!
Collaborative: | Northwest Collaborative Planning & Implementation Group
Meeting Type: | Monthly Collaborative Convening
Date: | Tuesday, July 16, 2024 | Location: | Zoom Link
Time: | 1:00 – 2:00 PM | Facilitator: | Population Health Innovation Lab, Public Health Institute
High Level Agenda
| Topic | Key Questions
Welcome, Framing, & Check-In
| Update from Partnership HealthPlan of California | What updates from PHC impact existing and prospective ECM and Community Supports processes?
Community Supports Question
| CalAIM Policy Landscape | How might the PHIL's PATH CPI Policy Resource enhance your organization's awareness of upcoming ECM/Community Supports policies and other updates related to CalAIM?
| Guest Speaker: TA Marketplace | How is the PATH Technical Assistance (TA) Marketplace currently being utilized in your county? How might your organization leverage the TA Marketplace to enhance CalAIM implementation?
Evaluation and Close
New Action Items (Identified this Meeting)
No. | Action Item | Owner | Created | Deadline | Status
1. | Collaborate with the TAM team to increase transparency around TAM recipients in the Northwest region. | PHIL | 2024-07-16 | 2024-12-31 | In Progress
Open Action Items
No. | Action Item | Owner | Created | Deadline | Status
1. | Partner with the Prevention Policy Group at the Public Health Institute to learn more about the Community Reinvestment Funds and share details and opportunities with PATH CPI participants. | PHIL | 2024-06-18 | 2024-12-31 | In Progress
2. | The PHIL team is updating their CPI webpage to include the new Theory of Change and Readiness Roadmap. | PHIL | 2024-06-18 | 2024-08-30 | In Progress
3. | PHIL plans to share more information on the updated Community Supports landscape and the new transitional rent program. | PHIL | 2024-06-18 | 2024-08-30 | In Progress
4. | Partner with NCHIIN to more broadly share their successful development and pilot of an integrated ECM Module within their Community Information Exchange (CIE), which uses the NinePatch® Whole Person Care SDOH Solution platform. | PHIL | 2024-05-21 | 2024-08-31 | Ongoing
5. | Partner with NCHIIN to support their community discovery work, which will focus on understanding the need for a local/regionalCalAIM administrative hub, and will help determine if a hub can help develop CalAIM providers and services in the region. | PHIL | 2024-05-21 | 2024-11-30 | Ongoing
6. | Meet with NCHIIN and Humboldt 211, which support local service provider information and referral networks, to explore how they might strengthen knowledge and informaton sharing across local organizations in order to increase CalAIM community-based referrals and service utilization. | Program Manager | 2024-03-25 | 2023-04-30 | In Progress
7. | Integrate the issue of confident and confidential care coordination into future programming. | Program Associate II and Program Manager | 2024-02-27 | 2024-05-01 | Incomplete
8. | Follow up with Action Items identified during the Ecosystems Activity | CPI participants with Program Manager support | 2024-02-27 | 2024-03-15 | Partially complete and in progress
9. | Invite K'ima:w Medical Center as a spotlight organization so they could share more abour their journey to becoming a ECM and Community Supports provider. | Program Associate II | 2024-02-27 | 2024-03-10 | Pending response
10. | Begin program development of the "Administrative Burden" Test of Change. This includes conducting a landscape assessment to learn the general understanding of hub models and glean regional interest. | Program Manager | 2024-01-26 | 2024-04-20 | In Progress
11. | Schedule meeting with NCHIIN and Arcata House to learn about the pilot program. | PHIL | 11/15/2023 | 3/30/2024 | In Progress
Ongoing Action Items
No. | Action Item | Owner | Created | Deadline | Status
1. | Continue the core work of the PATH CPI initiative to outreach and support CalAIM contract development, strengthen community-based referral, and monitor access to and utilization of CalAIM services. | PHIL | 2024-04-22 | Continuous | Ongoing
2. | Monitor referral progress to determine if additional community-based and provider referrals follow increased knowledge/awareness. | Program Manager with support of MERLIN | 2024-03-26 | Continuous | Ongoing
3. | Integrate tools for sustainability through the upcoming convenings, resources and conversations. | PHIL | 8/28/2023 | Continuous | Ongoing
4. | Integrate updated tools and resources in the Pre-Contract and Post-Contract Process, Tools, and Solutions packet. Share updates with collaboratives and CPI Facilitators as they become available. | PHIL | 8/28/2023 | Continuous | Ongoing
5. | Follow up with organizations who show great and minimal progress along the Readiness Roadmap for support and guidance. | PHIL | 6/29/2023 | Continuous | Strategizing
6. | Re-vamp website with developing resource and information needs to continue serving current and prospective CPI participants | PHIL | 5/30/2023 | Continuous | Implementing
7. | Develop collaborative systems improvement strategies. | PHIL | 4/21/2023 | Continuous | Strategizing
8. | Identify specific capacity building training. | PHIL | 4/21/2023 | Continuous | Outlined and finalizing
9. | Network and relationship building with new members added to the asset maps. | PHIL | 4/21/2023 | Continuous | Strategizing
10. | Identify existing coalitions, collaboratives and roundtables for ECM, Community supports | PHIL and CPI Partners | 3/30/2023 | Continuous | Data synthesized by mapping project will help to identify these initiatives.
11. | Recruitment of new CPI participants | PHIL and CPI Partners | 1/1/2023 | Continuous | Implementing
Closed Action Items
No. | Action Item | Owner | Created | Deadline | Status
1. | Coordinate with Partnership HealthPlan to co-facilitate a training for their QIP program measurements, dependent on the needs of participants. (See Lessons Learned) | Program Manager and Program Associate II | 2024-04-22 | 2024-05-03 | In Progress
2. | Host an ECM QIP training with Partnership HealthPlan of California as a "proof of concept" with the NW collaborative. Gather feedback, analyze the effectiveness of the training, and share the outcomes and conclusions with the collaborative and with other PATH CPI facilitators. | PHIL | 2024-05-21 | 2024-07-31 | In progress
3. | Coordinate with COTS to collect and share workplans, processes, and templates developed for their QIP program to CPI Participants via the PATH CPI website. | Program Associate II | 2024-04-22 | 2024-04-22 | Pending
4. | Adjust the timing of monthly meetings based on participants' preferences. | Program Associate II | 2024-03-22 | 2023-04-15 | Complete
5. | Evaluate and explore the notion of feasibility, sustainability and braided funding in upcoming Northwest PATH CPI Programming | Program Manager | 2024-02-27 | 2024-05-01 | Completed
6. | Coordinate with Camden Coalition on when to debut the "Go, No Go Feasibility Tool" | Program Associate II | 2024-02-27 | 2024-03-10 | Complete
7. | Several questions emerged about Administrative Hubs/Care Hubs – policy follow up with PHC, PCG/DHCS to inform future CPI participant trainings. | Program Manager | 2024-02-27 | 2024-03-10 | Completed
8. | Follow up with Native Spirit Consulting to learn how PHIL could be of support and service to organizations interestested in participating in CalAIM. | Program Associate II and Program Manager | 2024-02-27 | 2024-03-10 | Completed
9. | Revise the Theory of Change and share updates with the Northwest CPI Collaborative. | Program Associate II | 2024-02-27 | 2024-03-10 | Complete
10. | Follow up with Arcata House Partnership to learn how they are increasing clients, as some organizations are having difficulty with receiving referrals and large enough case loads to be sustainable. | Program Associate II | 2024-02-27 | 2024-03-10 | Complete
11. | PHIL will develop and distribute a flyer that shares an overview of CPI Facilitators Required Activities, as well as contact information for the programs administrators. This will be distributed as an email to the convenings attendants, and will be shared on the PATH CPI website. | Program Associate II | 2024-01-24 | 2024-01-29 | Complete
12. | PHIL will develop and distribute an "Action Lever Reference Guide" that shares an overview of DHCS Action Levers. This will be distributed as an email to the convenings attendants, and will be shared on the PATH CPI website. | Program Manager | 2024-01-25 | 2024-01-29 | Complete
13. | Develop a Q&A document for questions that were not answered. Once answered, the Q&A document will be sent to participants and will be added to the Readiness Roadmap website. | PHIL | 12/05/2023 | 12/15/2023 | Completed
14. | Ask Open Door Community Health Centers if we can share their CHW workflow. | PHIL | 12/05/2023 | 12/15/2023 | Completed
15. | Coordinate a conversation with PHC to learn how they can deliver updates regarding Birth Equity. | PHIL | 12/05/2023 | 12/15/2023 | Incomplete
16. | Support conversations between local HIE and DHCS to learn more about the “Closed Loop Referral System”. | PHIL | 12/05/2023 | 12/15/2023 | Complete
17. | Learn how HealthBegins is supporting their collaboratives with Case Consulting. | PHIL | 11/01/2023 | 11/15/2023 | Complete
19. | Uplift provider concerns DHCS’ marketing strategies for ECM and CS. | PHIL | 11/01/2023 | 11/15/2023 | Complete
20. | Issue Tracker additions: - Accessibility to tools from PHC including z codes, g code sheets, and eligible participant lists. - ECM and/or CS implementation barriers unique to school-based clinics. | PHIL | 8/28/2023 | 9/15/2023 | Completed
21. | Mapping care coordination processes. | PHIL | 6/29/2023 | 8/5/2023 | No longer a priority of the collaborative
22. | Propose monthly meetings with Camden, HC2, HealthBegins and Partnership to efficiently collate common issues among CPI collaboratives across Northern California counties | PHIL | 5/30/2023 | 6/5/2023 | Completed
23. | Strategize methods of collecting the step all participants are at on the Readiness Roadmap (polled during meetings as well as follow-up conversations) | PHIL | 4/21/2023 | 5/5/2023 | Completed
24. | A report of the initial Asset Mapping Survey findings is to be shared with the participants on the website. | MERLIN | 4/21/2023 | 6/5/2023 | Completed
25. | Incorporating charter feedback | PHIL | 1/1/2023 | 3/31/2023 | Completed
26. | PATH CPI Asset Mapping Survey | PHIL | 1/1/2023 | 5/15/2023 | Completed

## Meeting Summary
Key Takeaways & Discussion Themes by Agenda Topic
Topic | Discussion Themes/Key Takeaways | Actions Taken/Next Steps | Best Practices/Lessons Learned
Welcome | NA | NA | NA
Update from Partnership HealthPlan of California | Discussion Themes: Partnership Health Plan encouraged participants to register for and attend monthly ECM and CS Roundtable meetings. Partnership Health Plan will also be merging its Enhanced Care Management (ECM) and Community Supports (CS) departments. Key Takeaways: Participants are encouraged to attend monthly Roundtable meetings and participants should stay tuned for updated on the new, combined ECM and CS department. | NA | NA
Community Supports Update | Discussion Themes: The PHIL Team provided more information on the new Transitional Rent community supports offering. Key Takeaways: Three participants showed interest and intention to offer the Transitional Rent community support. | NA | NA
CalAIM Policy Landscape | Discussion Themes: The PHIL team provided an overview of the recently released Resource and Policy Guide. There were also policy updates related to dual-eligible members long-term services and support as well as long-term care populations of focus. |  | Lessons Learned: As of Monday July 22, all participants who have responded to the post-event survey indicated that they strongly agreed to the statement: "I am confident that I will utilize the PATH CPI Policy and Resource Guide to increase my awareness of the current CalAIM policy landscape and its implication on service providers."
Guest Speaker: TA Marketplace | Discussion Themes: Jenna Wahl, the TA Marketplace (TAM) Lead, provided an overview of the recently updated TAM. Jenna's presentation covered the following information: overview of the TAM, growth and success, tips and resources, and walkthrough of the website. Key Takeaways: Participants indicated a desire to better understand who has received TAM support in the region. Jenna shared the following: Del Norte County has one approved TAM recipient and Humboldt County has three approved TAM recipients. | Action Items: Collaborate with the TAM team to increase transparency around TAM recipients in the Northwest region. | Lessons Learned: Participants indicated a desire to better understand who has received TAM support in the region so they can connect and learn from these partners. Increased transparency will ideally impact applications for TAM services.
Evaluation and Close | NA | NA | NA
Identified Gaps/Challenges in CalAIM/ECM/Community Supports
Topic | Gaps/Challenges Identified | Actions Taken/Next Steps | Best Practices/Lessons Learned
TA Marketplace | Participants indicated a desire to better understand who has received TAM support in the region so they can connect and learn from these partners. | Collaborate with the TAM team to increase transparency around TAM recipients in the Northwest region. | Increased transparency may increase the number of applications and uptake of TAM services.
Identified Successes Experienced by Participants
Topic | Successes Identified | Actions Taken/Next Steps | Best Practices/Lessons Learned
Summary of Complaints & Grievances
Topic | Summary of Complaint/Grievance | Actions Taken | Next Steps
MCP Engagement (List all MCPs who should be engaged regardless of attendance) |  |  |  | KEY
MCP Name | Current Status of Relationship | MCP Engagement in Collaborative | Engagement Concerns & Notes | Acceptable | MCP attends 50%-75% collaborative convenings, MCP is responsive to collaborative requests but follow up is needed by facilitator
| i.e. Excellent > Acceptable > Needs Improvement > In Direct Contact With > No Contact | Yes/No |  | Excellent | MCP is engaged in collaborative, MCP attends 75%-100% collaborative convenings, MCP is presenter during collaborative meetings, MCP provides feedback and data where applicable, MCP works in partnership with facilitator and collaborative
Partnership HealthPlan | Excellent | Yes | NA | In Direct Contact With | Facilitator has direct contact with MCP, MCP may not currently be attending collaboratives, MCP may be transitioning in 2024 and not yet active in collaborative
|  |  |  | Needs Improvement | MCP is not or inconsistently engaged in collaborative, MCP attends 0%-25% of collaborative convenings, difficulties consulting with MCP, further partnership and relationship building is required
|  |  |  | No Contact | There is no contact with MCP, MCP is not present for collaborative meetings, no relationship built with MCP
Shared Collaborative Resources
Resource | Category/Type | Link/Access Information
PATH CPI | Website | https://pophealthinnovationlab.org/projects/path/
Native Lands | Website | https://native-land.ca
Partnership HealthPlan of California ECM Roundtable | Webinar | https://bit.ly/4cmy8Q2
Partnership HealthPlan of California Community Supports Roundtable | Webinar | https://bit.ly/3vhc34b
Policy and Resource Guide | Report | https://pophealthinnovationlab.org/projects/path/path-cpi-resources/
PATH CPI Feedback Form | Survey | https://corexms9fmhcw4nh6y8v.qualtrics.com/jfe/form/SV_6WDTBk9ZsjpxCJM
TA Marketplace | Website | https://www.ca-path.com/ta-marketplace/learn-tam
DHCS Listserv | Listserv | https://apps.dhcs.ca.gov/listsubscribe/default.aspx?list=BHTTRANSFORMATION%22%20%5Co%20%22https://apps.dhcs.ca.gov/listsubscribe/default.aspx?list=bhttransformation%22%20%5Ct%20%22_blank
July BHT Public Listening Session | Webinar | https://deloitte.zoom.us/webinar/register/WN_kVWacL29RziqSOGXLgwdeg#/registration
Office Hours Registration | Webinar | https://pophealthinnovationlab-org.zoom.us/meeting/register/tZ0qcO6qqT4uHddqXe9IGtzCUxZ31t1ZaF4v#/registration
Evaluation Survey | Survey | https://bit.ly/3Y4gA6t

## Meeting Attendance
Note: If your office hours were combined with another collaborative or facilitator group, please complete columns D & E.
Organization Name | Participant Name | Email | Collaborative Group | Facilitator Group
DHHS - County of Humboldt, California | Aaron Zell | azell@co.humboldt.ca.us | Northwest | Population Health Innovation Lab
Partnership HealthPlan | Ashley Peel | apeel@partnershiphp.org | Northwest | Population Health Innovation Lab
Partnership HealthPlan | Bianca Veneracion | bveneracion@partnershiphp.org | Northwest | Population Health Innovation Lab
Performance Kitchen | Brent Byler | bbyler@performancekitchen.com | Northwest | Population Health Innovation Lab
NCHIIN | Chris Davis | cdavis@nchiin.org | Northwest | Population Health Innovation Lab
FFPSA | Cindy Sutcliffe | csutcliffe@co.humboldt.ca.us | Northwest | Population Health Innovation Lab
PCG | Elise Memmo | ememmo@pcgus.com | Northwest | Population Health Innovation Lab
Arcata House | Erin Hall | ehall@arcatahouse.org | Northwest | Population Health Innovation Lab
Population Health Innovation Lab | Esmeralda Salas | esalas@phi.org | Northwest | Population Health Innovation Lab
Serene Health | Hector Medina | hector@serenehealth.com | Northwest | Population Health Innovation Lab
Mom's Meals | Isabella Bunkers | isabella.bunkers@momsmeals.com | Northwest | Population Health Innovation Lab
PCG | Jenna Wahl | jwahl@pcgus.com | Northwest | Population Health Innovation Lab
SacValley MedShare | Jennifer Inden | jennifer.inden@sacvalleyms.org | Northwest | Population Health Innovation Lab
Population Health Innovation Lab | Jessica Sanchez | jsanchez2@phi.org | Northwest | Population Health Innovation Lab
Sutter Health | Jodi Nerell | jodi.nerell@sutterhealth.org | Northwest | Population Health Innovation Lab
Del Norte Mission Possible | John Barnts | jbarnts@dnmissionpossible.org | Northwest | Population Health Innovation Lab
Humboldt NeuroHealth | Jonathan Marshall | jon@humboldtneurohealth.org | Northwest | Population Health Innovation Lab
K'ima:w Medical Center | Julia Hostler | julia.hostler@kimaw.org | Northwest | Population Health Innovation Lab
Population Health Innovation Lab | Kathryn Stewart | kathryn.stewart@phi.org | Northwest | Population Health Innovation Lab
Population Health Innovation Lab | Katie Christian | kchristian@phi.org | Northwest | Population Health Innovation Lab
Community Support Network | Kym Centaro | kym@csn-mh.com | Northwest | Population Health Innovation Lab
Balance | Lara Brecher | lbrecher@balancepro.org | Northwest | Population Health Innovation Lab
Independent Living Systems | Lorena Ahumada | lahumada@ilshealth.com | Northwest | Population Health Innovation Lab
Unite Us | Marisol Sifuentes | marisol.sifuentes@uniteus.com | Northwest | Population Health Innovation Lab
Population Health Innovation Lab | Megan Kenney | mkenney@phi.org | Northwest | Population Health Innovation Lab
Hospital Council - Northern & Central California | Meghan Hardin | mhardin@hospitalcouncil.org | Northwest | Population Health Innovation Lab
Humboldt County | Morgan Brannon | mbrannon@co.humboldt.ca.us | Northwest | Population Health Innovation Lab
Humboldt Senior Resource Center | Rachael Sovereign | rsovereign@humsenior.org | Northwest | Population Health Innovation Lab
Housing Outreach and Mobile Engagement- Humboldt County | Raul Torres | rtorres@co.humboldt.ca.us | Northwest | Population Health Innovation Lab
Open Door Health | Sandra Miliotti | smiliotti@opendoorhealth.com | Northwest | Population Health Innovation Lab
PCG | Sean Hanwell | shanwell@pcgus.com | Northwest | Population Health Innovation Lab
Population Health Innovation Lab | Seun Aluko | saluko@phi.org | Northwest | Population Health Innovation Lab
Hartsfield Consulting | Stefani Hartsfield | stefani@hartsfieldhealth.com | Northwest | Population Health Innovation Lab
Population Health Innovation Lab | Sue Grinnell | sgrinnell@phi.org | Northwest | Population Health Innovation Lab
Population Health Innovation Lab | Tammy Chandler | tchandler@phi.org | Northwest | Population Health Innovation Lab
Partnership HealthPlan | Vicky Klakken | vklakken@partnershiphp.org | Northwest | Population Health Innovation Lab
AHP (The Pathway) | Virginia Beckman | thepathway@arcatahouse.org | Northwest | Population Health Innovation Lab

## Lists (hidden)
Meeting Type
Monthly Collaborative Convening
Office Hours